## READ ME
Temptation Token — Sell This Software Plan v2 (Sept 25, 2026)
Built on the Sept 19 agency workbook. Every Sept 19 tab is kept (Targets, Scoring Model, Events, EV Calculator); the sale-plan tabs are new. Sender identity for all TTS correspondence: jim@temptationtoken.io.
DASHBOARD
Offer review date
Days until offer review
Plan tasks
Plan tasks marked Done
Plan completion
Acquirers on the list
Acquirers with a meeting booked or later
Agencies on the Sept 19 target list
HOW THE AUTOMATION WORKS
1. Plan tab = the master schedule (ET). The same tasks are in TTS_Sale_Plan_Proton.ics (import into Proton Calendar) and tasks.json (feeds the 7:00 AM daily email).
2. Daily email: tts_daily_digest.py runs on your Mac every morning at 7:00 AM ET through Proton Mail Bridge and sends today's tasks + tomorrow's preview + live numbers.
3. Status column (Plan, Acquirers): pick from the dropdown. The dashboard above counts it.
4. Owners: Jim = only you can do it. Jim + Mike = both signatures. Claude Code = runs on your Mac from the sprint prompt. Auto = scheduled, nothing to do.
LEGEND
Blue text = inputs you can change. Black = formulas or fixed text. Yellow fill = verify or fill in. Orange rows on Plan = launch day and offer day.
CONTACT RULES (kept from Sept 19)
Only business contacts from public sources are listed. 'Not published' means no public source was found — the Other routes column gives the legitimate way in (forms, LinkedIn, Impressum, Companies House, state registries). No personal numbers or home addresses, by design.
Canada (ManyVids): no cold email under CASL — LinkedIn or phone only. UK/EU: B2B email with a clear identity and opt-out. US: CAN-SPAM footer with the LLC postal address.
WHAT CHANGED IN V2 (SEPT 25)
Corrected against the overnight onchain verification: the token is immutable (not a proxy), supply is governed by the 2-of-2 Safe, no blacklist is possible, the timelock is a closing-day option rather than executed, and there is no paid audit before an offer. New tasks T66-T75 (WordPress fixes, Bridge password, footer address, audit-finding map, LINK recovery, replacement-cost sheet, traction push, scanner update, walk-away price). Email 1 and the Strengths, Audit & Liquidity, Data Room and Closing tabs were rewritten to match.
WHAT CHANGED SINCE SEPT 19
New tabs: Plan, Acquirers, Sequence, Scripts, Strengths, Platforms, Store Plan, Audit & Liquidity, Data Room, Closing. The old Send Schedule tab is replaced by Plan (sale mode). The Targets tab keeps all agencies for weekly enlistment — every enrolled agency is demand evidence for the sale.

## Plan
ID | Date | Day | Time (ET) | Owner | Workstream | Task | How / detail | Status | Done on | Notes
T01 | 2026-09-24 |  | 20:00 | Jim | OPS | Turn on Telegram two-step verification | On the Telegram account that owns @TemptationTokenBot and the channels: Settings > Privacy & Security > Two-Step Verification. Starts the 7-day clock Telegram requires before a bot can change owners. Do not change the password afterward. | Not started
T02 | 2026-09-24 |  | 20:15 | Jim | LEGAL | Send Mike the member consent + Safe-signer agreement | Written consent to sell (assets or the LLC) plus his agreement to sign the Safe transfer at close. Checklist: Data Room tab. | Not started
T03 | 2026-09-24 |  | 21:00 | Jim | OPS | Paste the Claude Code sprint prompt and let it run overnight | File: TTS_Sale_Sprint_ClaudeCode.md. Opens the site to crawlers, generates the AI Models batch, fork-tests the liquidity move, runs the pre-audit, installs the daily reminder email. | Not started
T04 | 2026-09-25 |  | 07:00 | Auto | OPS | First daily digest email arrives | Starts once the Bridge password is in .env (T67). Then every day at 7:00 AM ET through Nov 6. | Not started
T66 | 2026-09-25 |  | 07:30 | Jim | SITE | Fix the 7 false claims on WordPress - '45% APR' first | Replacement text: outputs/site/false_claims_2026-09-25.md. Edit each page by hand in WP admin / Elementor (revision-safe). If a page takes more than 5 minutes, set it to Draft until it's fixed. | Not started
T67 | 2026-09-25 |  | 08:00 | Jim | OPS | Put the Proton Bridge password into .env | Bridge app > your account > copy the Bridge password (not your Proton login) into Claude Code's masked prompt. Unblocks the daily email, the canary and all outreach. | Not started
T68 | 2026-09-25 |  | 08:15 | Jim | LEGAL | Choose the postal address for TTS email footers | CAN-SPAM needs a valid postal address. A USPS P.O. box or a virtual mailbox for Blockchain Entertainment LLC keeps your home and other businesses off TTS mail. Give it to Claude Code. | Not started
T05 | 2026-09-25 |  | 08:30 | Jim | STORE | Check Google Play account type | Play Console > Settings > Developer account > Account details. Personal (created after Nov 13, 2023) = 14-day closed test with 12+ testers first. Organization = submit to production now. Tell Claude Code which. | Not started
T06 | 2026-09-25 |  | 09:00 | Jim | AUDIT | Optional: SolidProof quote request (quote only - no money before an offer) | The draft with disclosures is in outputs/sale/. A quote gives you a 'cost to certify' number for negotiation; fund an audit only if a serious buyer asks for one as a closing condition. | Not started
T07 | 2026-09-25 |  | 09:30 | Jim | LIQ | Transak: generate the PRODUCTION API key | Business verification is done, so pull the production key in the Transak dashboard and hand it to Claude Code through its secure prompt (never paste keys in chat). | Not started
T08 | 2026-09-25 |  | 10:00 | Jim | AI | Create an image-generation API key | Replicate, fal.ai or OpenAI. Add IMAGE_API_KEY to the repo .env. Costs pennies per image. | Not started
T69 | 2026-09-25 |  | 11:00 | Claude Code | AUDIT | Map the original audit's 1 critical + 3 high to the deployed code | Each one: fixed / not applicable / live. Anything live and exploitable = no card go-live until it's mitigated. Results go on /audit. | Not started
T09 | 2026-09-25 |  | 12:00 | Jim | LIQ | Read the liquidity fork-test report | outputs/sale/liquidity_forktest.md: card-buy sizes before/after, price impact, and exactly what Safe transaction #1 does. | Not started
T10 | 2026-09-25 |  | 13:00 | Jim + Mike | LIQ | Sign Safe transaction #1: liquidity | Built and fork-verified: new pool, tax exemption, single-sided position funded with 0.0101% of the Safe's TTS - no ETH, no cash. Max card buy goes from ~$50 to $1,000 ($500 at 1.92% impact, $1,000 at 3.26%). Expires Oct 9 - rebuild if the price moves. | Not started
T70 | 2026-09-25 |  | 14:00 | Claude Code | LIQ | Recover the ~44 LINK - autopilot gate met | Rounds 9-12 settled unattended. Build the cancel/withdraw transaction(s); top the VRF subscription to 25+ LINK first; remainder to ETH for sell-side depth. | Not started
T11 | 2026-09-25 |  | 15:00 | Jim | AI | Approve the AI Models batch in admin | Approval queue in admin. Reject anything that looks under 25, any nudity, any resemblance to a real person. | Not started
T12 | 2026-09-25 |  | 16:00 | Jim | STORE | Personal Play account only: recruit 15-20 testers | Send the closed-test opt-in link from outputs/listings/play_closed_test.md. 12 must stay opted in 14 straight days; over-recruit so attrition never resets the clock. | Not started
T13 | 2026-09-25 |  | 17:00 | Jim | SITE | Verify temptationtoken.io in Google Search Console + Bing Webmaster | DNS TXT record at the registrar, then import the site into Bing Webmaster Tools. Unlocks the traffic data buyers ask for. | Not started
T14 | 2026-09-26 |  | 10:00 | Claude Code | SITE | WordPress plugin v1.2 + robots.txt check | Authenticated write routes for posts, pages and options so Claude Code can maintain the site. Also print temptationtoken.io/robots.txt as served and remove any AI-crawler Disallow lines. | Not started
T71 | 2026-09-26 |  | 11:00 | Claude Code | DATA | Replacement-cost sheet for the data room | What it would cost a buyer to build this - components, hours at market rates, calendar time - from git history. Backs the asking price. | Not started
T15 | 2026-09-26 |  | 14:00 | Jim | SITE | Upload plugin v1.2 in WP admin (Plugins > Add New > Upload) | Two minutes. Unlocks API edits to the site from then on. | Not started
T16 | 2026-09-27 |  | 11:00 | Jim | DATA | Record the 2-3 minute Loom demo | Board > Face ID signup > vote > trophy on Basescan > admin > club signup > AI Models division. Paste the link into LOOM_URL. | Not started
T17 | 2026-09-27 |  | 18:00 | Jim | DATA | Review the data room draft | outputs/sale/data_room/ - mark anything to add. | Not started
T18 | 2026-09-28 |  | 07:00 | Auto | AI | AI Models rotation #1 | Runs after the round settles. Retires the oldest AI entries, activates the next approved batch; one extra retires for each new verified creator. | Not started
T19 | 2026-09-28 |  | 09:00 | Claude Code | AUDIT | Build + fork-test the 48-hour timelock package - do NOT execute | Parked as a closing-day option for the buyer. Handing admin to a timelock on an immutable token can't be undone, so it happens only if the buyer wants it. | Not started
T20 | 2026-09-28 |  | 10:00 | Jim | LIQ | Live card test: buy $30 of TTS by card on your phone | Only after T69 finds no live critical/high issue and Safe tx #1 has executed. Confirms Transak > swap > wallet end to end in production. | Not started
T21 | 2026-09-28 |  | 11:00 | Claude Code | SITE | IndexNow push + request indexing on the top 10 pages | Every URL goes to IndexNow engines within hours; Google via Search Console. | Not started
T72 | 2026-09-28 |  | 12:00 | Jim | OUTREACH | Traction push: post each round to your Telegram and X | Every real vote raises the price. Share the round link, the free first vote and the 500 TTS signup bonus. Real people only - buyers check onchain. | Not started
T22 | 2026-09-28 |  | 14:00 | Jim | STORE | Play: org account > submit production; personal > confirm 12+ testers opted in | Listing copy: outputs/listings/play_store_listing.md. | Not started
T23 | 2026-09-29 |  | 10:00 | Jim | OUTREACH | Register TTS on base.dev and submit the mini app form | Builder presence in the Base ecosystem; your paymaster already meets the sponsored-gas criterion. | Not started
T24 | 2026-09-29 |  | 11:00 | Jim | DATA | Approve the one-pager and listing drafts | outputs/sale/listings/ (Acquire.Fi, SideProjectors, IndieMaker). | Not started
T73 | 2026-09-29 |  | 11:00 | Claude Code | LIQ | Draft the Blockaid / GoPlus update for Jim to send | Evidence: the contract has no blacklist setter, plus the deeper liquidity from Safe tx #1. | Not started
T25 | 2026-09-29 |  | 14:00 | Jim | OUTREACH | LinkedIn: follow every decision-maker on the Acquirers tab | Warms up the Oct 1 connection requests. | Not started
T74 | 2026-09-29 |  | 16:00 | Jim + Mike | CLOSE | Agree your private walk-away price | Anchors stay $95K structured / $65K all-cash. The floor stays between you two and off every document. | Not started
T26 | 2026-09-30 |  | 10:00 | Jim | LEGAL | Put counsel's sign-off letter in the data room | Send counsel a short note first that the old site claims were found and corrected (with dates) so the letter reflects the current site. One page confirming the review is complete. | Not started
T27 | 2026-09-30 |  | 11:00 | Claude Code | SITE | Final QA: crawler test per bot, speed, schema, links | Report: outputs/site/qa_final.md. | Not started
T28 | 2026-09-30 |  | 16:00 | Jim | OUTREACH | Approve the Oct 1 automated batch | Claude Code queues each email for 9:05 AM recipient-local time; a canary copy to you fires first. | Not started
T29 | 2026-10-01 |  | 09:05 | Auto | OUTREACH | LAUNCH - Email 1 to AROA + RCI investor relations | office@aroaagency.com; gfishman@pondel.com + mwichman@pondel.com. SheX goes at 3:05 AM ET (9:05 Berlin) once the Impressum address is verified. | Not started
T30 | 2026-10-01 |  | 09:30 | Jim | OUTREACH | Submit listings: Acquire.Fi, SideProjectors, IndieMaker | Same one-pager everywhere. Offers reviewed Fri Oct 16. | Not started
T31 | 2026-10-01 |  | 10:00 | Jim | OUTREACH | Contact forms: Creators Inc, Fanvue, Infloww, The Clueless | Paste Email 1 with each company's hook (Scripts tab). | Not started
T32 | 2026-10-01 |  | 10:30 | Jim | OUTREACH | LinkedIn connection requests with note | Monange, Fitzgerald, Morris (Fanvue); Bachman (Creators Inc); Langan (RCI); Cruz (The Clueless); Etelis (Fansly); French (ManyVids); Bouslama (Acquire.Fi). | Not started
T33 | 2026-10-01 |  | 12:30 | Jim | OUTREACH | DMs: Instagram, Telegram, X | IG: @creatorsinc / Andy Bachman, @tonyizzet, Louna. Telegram: t.me/supercreator_app. X: @Acquire_Fi. | Not started
T34 | 2026-10-02 |  | 10:00 | Jim | OUTREACH | Reply to every response within an hour; book calls | calendly.com/temptationtoken/phone-meeting. Screen-share the live app, not slides. | Not started
T35 | 2026-10-02 |  | 12:30 | Jim | OUTREACH | Telegram follow-up to AROA | t.me/aroaagency1 - one line + the Loom. | Not started
T75 | 2026-10-03 |  | 10:00 | Claude Code | SITE | Optional: site rebuild on staging (same look) | Only after every public claim is true. Buyers forgive a dated layout, not a false claim. | Not started
T36 | 2026-10-05 |  | 07:00 | Auto | AI | AI Models rotation #2 | Automatic after settlement. | Not started
T37 | 2026-10-05 |  | 10:00 | Jim | OUTREACH | Weekly results note to engaged buyers | Round winner, votes, new creators, pool depth, card buys. Claude Code drafts it from live data. | Not started
T38 | 2026-10-06 |  | 09:05 | Auto | OUTREACH | Email 2 (proof + data room under NDA) to AROA + RCI IR | Includes the Loom and what shipped since Oct 1. | Not started
T39 | 2026-10-06 |  | 10:00 | Jim | OUTREACH | Email 2 via LinkedIn messages and forms | Same content to every accepted connection and form contact. | Not started
T40 | 2026-10-07 |  | 10:30 | Jim | OUTREACH | Call RCI investor relations: 212-883-0655 | Ask who evaluates digital partnerships or acquisitions; send a same-day recap email. Script: Scripts tab. | Not started
T41 | 2026-10-07 |  | 11:30 | Jim | OUTREACH | One-line follow-up DMs to non-responders | Line + Loom link. | Not started
T42 | 2026-10-08 |  | 18:00 | Jim | OUTREACH | Visit 2-3 clubs from your club list with the /clubs QR | Goal: signed-up clubs = demand evidence for the data room. Optional: Rick's Cabaret New York, 50 W 33rd St - ask for the GM and a corporate intro. | Not started
T43 | 2026-10-09 |  | 09:00 | Jim | STORE | Personal Play account: closed test hits 14 days - apply for production | Answers: outputs/listings/play_production_answers.md. | Not started
T44 | 2026-10-09 |  | 12:00 | Jim | AUDIT | Check SolidProof status; answer any questions same day |  | Not started
T45 | 2026-10-12 |  | 07:00 | Auto | AI | AI Models rotation #3 | Automatic after settlement. | Not started
T46 | 2026-10-12 |  | 09:05 | Auto | OUTREACH | Email 3 ('offers reviewed Friday') to AROA + RCI IR | Jim sends the same note via LinkedIn/forms at 10:00. | Not started
T47 | 2026-10-13 |  | 10:00 | Jim | DATA | Open the data room to every buyer who signed the NDA | Track who opened what - interest signal. | Not started
T48 | 2026-10-14 |  | 12:00 | Claude Code | AUDIT | Refresh the /audit status table (every finding vs. the deployed code) | Replaces the 'publish a new audit' step - no pre-sale audit purchase. | Not started
T49 | 2026-10-15 |  | 17:00 | Jim | OUTREACH | Last-call note to engaged buyers | 'Reviewing offers tomorrow at 5 PM ET.' | Not started
T50 | 2026-10-16 |  | 17:00 | Jim + Mike | CLOSE | OFFERS REVIEW | Rank by total value, cash at close, earn-out terms, certainty, speed. Best structure beats biggest headline. | Not started
T51 | 2026-10-19 |  | 07:00 | Auto | AI | AI Models rotation #4 | Automatic after settlement. | Not started
T52 | 2026-10-19 |  | 10:00 | Jim | CLOSE | Counter/accept, sign the LOI, engage the lawyer | Asset purchase vs. LLC purchase per CPA advice. | Not started
T53 | 2026-10-21 |  | 10:00 | Jim | CLOSE | Open escrow; buyer deposit |  | Not started
T54 | 2026-10-23 |  | 10:00 | Jim | CLOSE | Buyer diligence Q&A session | Data room + live walkthrough. | Not started
T55 | 2026-10-25 |  | 09:00 | Jim | OPS | Clock change: UK/EU fell back - London is ET+4 until Nov 1 |  | Not started
T56 | 2026-10-26 |  | 07:00 | Auto | AI | AI Models rotation #5 | Automatic after settlement. | Not started
T57 | 2026-10-26 |  | 10:00 | Claude Code | CLOSE | Transfer rehearsal on a fork | Safe owner swap, role moves, bot transfer checklist, project transfers - dry run. | Not started
T58 | 2026-10-28 |  | 10:00 | Jim + Mike | CLOSE | Sign the purchase agreement |  | Not started
T59 | 2026-11-01 |  | 09:00 | Jim | OPS | Clock change: US fell back - all times now EST |  | Not started
T60 | 2026-11-02 |  | 07:00 | Auto | AI | AI Models rotation #6 (skip if closed) |  | Not started
T61 | 2026-11-02 |  | 10:00 | Jim | CLOSE | Escrow funded - start transfers per the runbook | Closing tab, in order. | Not started
T62 | 2026-11-03 |  | 10:00 | Jim + Mike | CLOSE | Transfers day 1: Safe owner swap + roles + treasury to buyer wallets | Onchain moves only - never hand over keys or seed phrases. | Not started
T63 | 2026-11-04 |  | 10:00 | Jim | CLOSE | Transfers day 2: domains, hosting, repo, cloud projects, Expo/Play, Telegram bot |  | Not started
T64 | 2026-11-05 |  | 10:00 | Claude Code | CLOSE | Rotate every key and secret; verify buyer controls everything |  | Not started
T65 | 2026-11-06 |  | 12:00 | Jim | CLOSE | Buyer confirms receipt - escrow releases funds | Sale closed. | Not started

## Acquirers
ID | Tier | Company | Category | HQ / time zone | Decision-maker(s) (public) | Title | Verified business contact (published) | Other routes | Visit / in person | Why they buy (strength framing) | Opening hook | Structure to lead with | Outreach law | Source(s) | Verified? | Status | Next step | Next date
A1 | 1 | Fanvue | Fan platform - AI-creator category leader | London (Canary Wharf) - ET+5 until Oct 25, then ET+4 until Nov 1 | Will Monange; Harry Fitzgerald; Joel Morris | Co-founder & CEO; Co-founder & COO; Co-founder | Business email not published in the sources checked | LinkedIn (all three founders); fanvue.com business contact; public developer API (integration angle) | London HQ by appointment; XBIZ LA Jan 7-10, 2027 | Built its growth on AI creators and runs the Miss AI pageant - TTS is a weekly onchain fan vote with a disclosed AI Models division next to verified creators, ready to plug into Fanvue's public API. | Miss AI proved fans will vote on AI creators. We run that vote every week, onchain, with an AI Models division beside verified creators. | Cash + earn-out tied to creators onboarded; or tech acquisition + 60-day consulting | UK PECR B2B: identify yourself, give an opt-out | BusinessWire Jan 12 2026 (Series A, founders' titles); Las Vegas Sun Jul 10 2026 ($200M run rate, CEO); Wikipedia/Fanvue (AI creators, Miss AI, public API 2025) | Names/titles: yes. Email/phone: not published | Not contacted
A2 | 1 | Creators Inc | OnlyFans management agency - largest roster found | Miami, FL - ET | Andrew (Andy) Bachman | Founder & CEO | Not published (site uses a contact form) | creatorsinc.com/contact form; Instagram @creatorsinc; weekly podcast (guest pitch); FL Sunbiz for the principal address (direct mail) | Miami Swim Week - CI Swimwear show (late May/early June) | 400+ creators. Owning the vote means owning a weekly traffic event for the entire roster instead of renting attention. | Your roster is the biggest audience in the category. The platform that turns it into a weekly event is built and running. | Cash + earn-out; or equity partnership | US CAN-SPAM | Sept 19 workbook (creatorsinc.com; Supercreator directory) | Name/title: yes. Email: not published | Not contacted
A3 | 1 | AROA Agency | OnlyFans management agency (multi-country) | Miami, FL (HQ) - ET | Not published - ask office@ for the partnerships lead by name | - | office@aroaagency.com (site footer, verified Sept 2026); 8101 Biscayne Blvd, Ph 703-24, Miami, FL 33138 | Telegram t.me/aroaagency1; aroaagency.com/uk/contact | XBIZ / AVN (attends) | Refer-Creators program = referral economics; TTS pays referral rewards onchain every week across a multilingual roster. | Your Refer-Creators program already runs on referral economics - this runs it onchain, weekly, for every creator you place. | Cash + earn-out | US CAN-SPAM | aroaagency.com/uk (Sept 19 verification) | Email + address: yes | Not contacted
A4 | 1 | Infloww | Agency software (OnlyFans CRM) moving into AI + fintech | London - ET+5 until Oct 25 | Not published - UK Companies House lists the directors | Director(s) | Not published | infloww.com contact; Companies House officer search; LinkedIn | - | Diversifying into AI tools and fintech - TTS is a finished fan-engagement + payments layer its agency customers can switch on. | You're building into AI and fintech. Here's a finished engagement-and-payments layer your agencies could turn on next month. | Cash acquisition of the engine + optional revenue share | UK PECR B2B | Company profile (London private limited, founded 2019, ~45 staff); WebCatalog (AI + fintech diversification) | Company facts: yes. Decision-maker: look up | Not contacted
A5 | 1 | Supercreator (supercreator.app) | Agency software + global agency directory | Tel Aviv - ET+7 | Co-founders Yuval and Amir (surnames not published in sources found) | Co-founders | Not published | Telegram t.me/supercreator_app; X @Supercreatorapp; consultation Calendly on supercreator.app | - | Their directory is the global agency list - TTS becomes a perk they hand every listed agency, or a product they own outright. | Your directory is where agencies live. This is a weekly traffic engine you could hand every one of them. | Cash + rev share on agencies onboarded | B2B with opt-out | Startup registry profile (founded 2022, Tel Aviv); Sept 19 workbook (channels) | Channels: yes. Full names: no | Not contacted
A6 | 1 | RCI Hospitality Holdings (NASDAQ: RICK) | Public club operator (60+ locations) | Houston, TX - ET-1 | Eric Langan | Chairman, President & CEO | Media & investor contacts (published Nov 2025): Gary Fishman & Michael Wichman, 212-883-0655, gfishman@pondel.com, mwichman@pondel.com | X @RCIHHinc; LinkedIn (Langan) | Rick's Cabaret New York, 50 W 33rd St, NYC (business venue) | 60+ venues whose customers want to be seen; the /clubs flow lets any venue run its own weekly fan vote from a phone - fan engagement that drives door traffic. | Your venues already sell the experience of being seen. This lets every club run a weekly fan vote from a phone and send fans back through the door. | Cash; or license + pilot across 5 venues | US CAN-SPAM | BusinessWire Nov 14 2025 (contacts; Langan title); RCI release Jan 2023 (60+ locations) | IR contacts: yes | Not contacted
A7 | 2 | The Clueless | AI-model agency (creator of Aitana Lopez) | Barcelona - ET+6 | Ruben Cruz | Co-founder & Creative Director | Not published in sources checked | theclueless.ai contact; LinkedIn | - | Runs AI talent that already earns on Fanvue - an AI Models division needs exactly their roster, and owning the stage beats renting it. | Aitana showed AI talent can build a real audience. We built the weekly stage where fans vote for it. | Cash or equity swap | EU GDPR B2B legitimate interest | Wikipedia/Aitana Lopez; Reason.Why (Cruz title); press on Fanvue presence | Name/title: yes | Not contacted
A8 | 2 | Fansly | Fan platform (bootstrapped) | Baltimore, MD (Select Media LLC) / Cyprus (CY Media LTD) - ET | Michael Etelis | Founder / owner | Not published | Maryland business registry (Select Media LLC address) for direct mail; LinkedIn; fansly.com business contact | - | Competes on creator features - a weekly spotlight that sends fans to creators' pages is a feature they can ship next week. | Fansly grew by giving creators a better home. This gives them a weekly spotlight that sends fans straight to their page. | Cash acquisition | US CAN-SPAM | Wikipedia/Fansly; MEL Magazine (ownership) | Name: yes. Contact: not published | Not contacted
A9 | 2 | ManyVids | Creator platform | Montreal - ET | Bella French | Co-founder (CEO title per Wikipedia infobox; verify current title) | Not published | LinkedIn; corporate phone if published on their site | - | Creator-first brand - a weekly fan-vote contest is an engagement feature that fits their residuals story. | You built ManyVids around fair pay for creators. This adds a weekly fan vote that pays creators in attention. | Cash acquisition | Canada CASL - NO cold email. LinkedIn or phone only | Wikipedia/ManyVids | Name: yes | Not contacted
A10 | 1 | Acquire.Fi | Web3 M&A marketplace (venue + buyer network) | Remote / BVI | Nassim Bouslama; Jan Strandberg | Co-founder & CEO; Co-founder & CTO | Seller form on acquire.fi | X @Acquire_Fi; LinkedIn | - | Web3 buyers who want a working onchain product with apps, entity and distribution - not a whitepaper. | - | Listed ask: $95K structured / $65K all-cash | - | CoinDesk profile (founders); G2 (marketplace scope) | Names: yes | Not contacted
A11 | 2 | Louna's Models | Agency - runs the Exclu Awards | Los Angeles - ET-3 | Louna | Founder | Not published | Instagram DM | Exclu Awards LA | Owns an awards event - a TTS-powered fan-vote award category turns into ownership of the vote itself. | Exclu Awards is the closest thing to what we run every week - except our vote is onchain. | Cash + partnership | US CAN-SPAM | Sept 19 workbook | Name: yes | Not contacted
A12 | 2 | Upbrand | Agency (Australia) | Australia - ET+14 (ET+15 after Oct 4) | Tony Izzet | Founder | Not published | Instagram @tonyizzet | - | Capacity-constrained ('all spots filled') - a self-running engine adds revenue without headcount. | Your bio says every spot is filled. This adds revenue per creator without adding a single hire. | Cash + earn-out | Australia Spam Act | Sept 19 workbook (Instagram) | Name: yes | Not contacted
A13 | 2 | SheX Agency | Agency (DACH, multi-platform) | Germany - ET+6 | Named in the Impressum (verify at she-x.de/impressum) | Geschaeftsfuehrer | Impressum email (legally required - Claude Code verifies before sending) | Instagram @onlyfans_agentur | - | Runs creators across several platforms, so off-platform promotion is already their model. | You already run creators across five platforms - this is the one that brings fans to all of them. | Cash + earn-out | EU GDPR B2B | Sept 19 workbook (Trustpilot, Instagram) | Route: yes | Not contacted
Tier 1 count
Tier 2 count
Structure note: list the full package at $95K structured (cash + earn-out) or $65K all-cash. The gap nudges buyers toward structure. Never lead with token price. Your private floor stays off every document.

## Sequence
Acquirer ID | Company | Date | Day | Time (ET) | Channel | Action | Script (Scripts tab) | Status
A13 | SheX Agency | 2026-10-01 |  | 03:05 | Email (auto) | Email 1 to the verified Impressum address (9:05 Berlin) | Email 1 - acquirer | Not started
A3 | AROA Agency | 2026-10-01 |  | 09:05 | Email (auto) | Email 1 to office@aroaagency.com | Email 1 - acquirer | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-01 |  | 09:05 | Email (auto) | Email 1 to gfishman@pondel.com + mwichman@pondel.com | Email 1 - acquirer | Not started
A10 | Acquire.Fi | 2026-10-01 |  | 09:30 | Listing form | Submit the Acquire.Fi seller form |  | Not started
A1 | Fanvue | 2026-10-01 |  | 10:00 | Web form | Email 1 + Fanvue hook via fanvue.com business contact | Email 1 - acquirer | Not started
A2 | Creators Inc | 2026-10-01 |  | 10:00 | Web form | Email 1 via creatorsinc.com/contact | Email 1 - acquirer | Not started
A4 | Infloww | 2026-10-01 |  | 10:00 | Web form | Email 1 via infloww.com contact | Email 1 - acquirer | Not started
A7 | The Clueless | 2026-10-01 |  | 10:00 | Web form | Email 1 via theclueless.ai | Email 1 - acquirer | Not started
A1 | Fanvue | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Monange, Fitzgerald, Morris | LinkedIn connection note | Not started
A2 | Creators Inc | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Andy Bachman | LinkedIn connection note | Not started
A4 | Infloww | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to directors found on Companies House | LinkedIn connection note | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Eric Langan | LinkedIn connection note | Not started
A7 | The Clueless | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Ruben Cruz | LinkedIn connection note | Not started
A8 | Fansly | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Michael Etelis | LinkedIn connection note | Not started
A9 | ManyVids | 2026-10-01 |  | 10:30 | LinkedIn | Connect note to Bella French (no cold email - CASL) | LinkedIn connection note | Not started
A10 | Acquire.Fi | 2026-10-01 |  | 12:30 | X | DM @Acquire_Fi with the one-pager link | DM | Not started
A11 | Louna's Models | 2026-10-01 |  | 12:30 | Instagram | DM Louna - award-category + ownership angle | DM | Not started
A12 | Upbrand | 2026-10-01 |  | 12:30 | Instagram | DM @tonyizzet | DM | Not started
A2 | Creators Inc | 2026-10-01 |  | 12:30 | Instagram | DM @creatorsinc + Bachman (podcast-guest + acquisition angle) | DM | Not started
A5 | Supercreator (supercreator.app) | 2026-10-01 |  | 12:30 | Telegram | DM t.me/supercreator_app + book the consultation Calendly | DM | Not started
A8 | Fansly | 2026-10-02 |  | 10:00 | Web form | Email 1 via fansly.com business contact | Email 1 - acquirer | Not started
A3 | AROA Agency | 2026-10-02 |  | 12:30 | Telegram | Nudge on t.me/aroaagency1 + Loom |  | Not started
A13 | SheX Agency | 2026-10-06 |  | 03:05 | Email (auto) | Email 2 | Email 2 - proof | Not started
A3 | AROA Agency | 2026-10-06 |  | 09:05 | Email (auto) | Email 2 (proof + data room) | Email 2 - proof | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-06 |  | 09:05 | Email (auto) | Email 2 (proof + data room) | Email 2 - proof | Not started
A1 | Fanvue | 2026-10-06 |  | 10:00 | LinkedIn | Email 2 (proof + data room) to accepted connections | Email 2 - proof | Not started
A10 | Acquire.Fi | 2026-10-06 |  | 10:00 | Email / X | Follow-up with Loom + audit status |  | Not started
A2 | Creators Inc | 2026-10-06 |  | 10:00 | IG / LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A4 | Infloww | 2026-10-06 |  | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A5 | Supercreator (supercreator.app) | 2026-10-06 |  | 10:00 | Telegram | Email 2 content (proof + data room) | Email 2 - proof | Not started
A7 | The Clueless | 2026-10-06 |  | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A8 | Fansly | 2026-10-06 |  | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A9 | ManyVids | 2026-10-06 |  | 10:00 | LinkedIn | Email 2 content via message | Email 2 - proof | Not started
A11 | Louna's Models | 2026-10-06 |  | 12:30 | Instagram | Proof DM with Loom | DM | Not started
A12 | Upbrand | 2026-10-06 |  | 12:30 | Instagram | Proof DM with Loom | DM | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-07 |  | 10:30 | Phone | Call IR at 212-883-0655 - ask who evaluates digital deals | Call opener | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-08 |  | 18:00 | Visit (optional) | Rick's Cabaret New York - GM demo + corporate intro | Club visit | Not started
A13 | SheX Agency | 2026-10-12 |  | 03:05 | Email (auto) | Email 3 | Email 3 - offer date | Not started
A3 | AROA Agency | 2026-10-12 |  | 09:05 | Email (auto) | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-12 |  | 09:05 | Email (auto) | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A1 | Fanvue | 2026-10-12 |  | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A2 | Creators Inc | 2026-10-12 |  | 10:00 | IG / LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A4 | Infloww | 2026-10-12 |  | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A5 | Supercreator (supercreator.app) | 2026-10-12 |  | 10:00 | Telegram | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A7 | The Clueless | 2026-10-12 |  | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A8 | Fansly | 2026-10-12 |  | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A9 | ManyVids | 2026-10-12 |  | 10:00 | LinkedIn | Offers reviewed Oct 16 |  | Not started
A1 | Fanvue | 2026-10-15 |  | 17:00 | LinkedIn | Last call (if engaged) | Call opener | Not started

## Scripts
Script | Text (fill {{FirstName}}, {{Company}}, {{Hook}} from the Acquirers tab) | Verified 2026-09-25 (Claude Code)
Email 1 - acquirer (Oct 1) | Subject A: Acquisition: a working onchain fan-voting platform Subject B: {{Company}} + a weekly fan-vote engine you could own Hi {{FirstName}}, {{Hook}} I'm Jim Goetz, founder of Temptation Token. We built a complete weekly fan-voting platform on Base: fans vote for creators, winners receive onchain trophies, and every creator's profile sends voters straight to her link hub. Working today: - Web app, Android app, Telegram bot - Face ID sign-up with gas-free wallets; card purchases through Transak - Weekly rounds that settle themselves onchain - every vote and winner publicly verifiable - Club self-serve onboarding, referral engine, automated social posting - An AI Models division, clearly labeled, ready for agency creators to join - Contracts verified on Base: supply governed by a 2-of-2 multisig, no blacklist function, full audit history disclosed - Delaware entity, domains, brand, and an SEO site that publishes automatically My other companies need my full attention, so Temptation Token needs a full-time owner. We're reviewing offers on Friday, October 16. If owning it makes sense for {{Company}}, I'll open the data room under NDA - 20 minutes is enough to see it live: calendly.com/temptationtoken/phone-meeting Jim Goetz Founder, Temptation Token - Blockchain Entertainment LLC jim@temptationtoken.io | [HOLDS] Trophies, onchain settlement and the profile link-out all verified.
Email 2 - proof (Oct 6) | Subject: 2-minute walkthrough + data room - Temptation Token {{FirstName}} - here's the platform running live: [LOOM_URL] New since last week: [SHIPPED_THIS_WEEK - e.g. card purchases live, deeper liquidity, audit underway, Round # settled] The data room covers contracts, round history, metrics, architecture, monthly running cost, and the transfer runbook. Reply 'NDA' and I'll send it today. Offers are reviewed Friday, October 16. Jim | [FIX] "audit underway" is NOT true — the SolidProof contact is quote-only by decision. Replace that example. Also: the data room's monthly cost sheet needs real invoice figures and the transfer runbook is a draft — finish both before Oct 6 or drop them from the sentence.
Email 3 - offer date (Oct 12) | Subject: Offers reviewed Friday - Temptation Token {{FirstName}} - a quick note that we're reviewing offers this Friday, October 16 at 5 PM ET. Cash, cash plus earn-out, and partnership structures are all on the table. If a 20-minute look would help before then: calendly.com/temptationtoken/phone-meeting Jim | [HOLDS] No factual claims to check.
LinkedIn connection note (300 chars max) | Jim Goetz, founder of Temptation Token - a working onchain fan-voting platform (web, Android, Telegram). We're reviewing acquisition offers Oct 16 and {{Company}} is a natural fit. Worth a 20-minute look? | [NEEDS EDIT] "(web, Android, Telegram)" — no Android build is published. Say "web and Telegram, Android in progress."
DM - Instagram / X / Telegram | {{FirstName}} - Jim Goetz, founder of Temptation Token. We built a weekly onchain fan vote: creators get a spotlight, fans vote, winners get trophies, and every profile sends fans to the creator's page. We're selling it to an owner with a roster - {{Company}} fits. Can I send the 2-minute walkthrough? | [HOLDS] Mechanic described accurately.
Call opener - RCI investor relations (Oct 7) | [STRUCK 2026-09-25 — see verification note] Hi Gary, Jim Goetz, founder of Temptation Token. I emailed you and Michael last week. We're selling a turnkey fan-engagement platform with a self-serve club program - any venue can run its own weekly fan vote from a phone. Who at RCI looks at digital partnerships or acquisitions? I'd like to get them a 20-minute demo before we review offers on the 16th. | [STRUCK] "self-serve club program — any venue can run its own weekly fan vote from a phone" is FALSE. Club registration is admin-only (requireAdmin on every write in api/set-club-wallet.js); pending_clubs and club_partners both have 0 rows. USE INSTEAD: "a club partner program wired on-chain — a club code links to a wallet and its 10% share pays automatically on settlement; registration is approved by us."
Voicemail (20 seconds) | Hi, it's Jim Goetz with Temptation Token - I sent a note about a weekly fan-vote platform we're selling to an owner with a roster or venues. The two-minute walkthrough is in your inbox; my email is jim@temptationtoken.io. We're reviewing offers October 16. Thanks. | [HOLDS] No factual claims to check.
Club visit (60 seconds) | [STRUCK 2026-09-25 — see verification note] Hi, I'm Jim Goetz with Temptation Token. We run a weekly fan vote for entertainers - your club can join from a phone in about two minutes, and it sends fans back through your door. Can I show you on my phone? [Scan the /clubs QR together.] | [STRUCK] "join from a phone in about two minutes" is FALSE for the same reason. Also temptationtoken.io/clubs returns 404, so "[Scan the /clubs QR together]" points at a dead URL — build the page or drop the QR step.
Placeholders | [LOOM_URL] = your demo link. [SHIPPED_THIS_WEEK] = Claude Code fills from live data. Claude Code verifies every line against chain and the live app before Oct 1 and strikes anything that doesn't hold. Never state a prize-pool dollar figure, token price, APR or return. | [NOTE] Verification done 2026-09-25 — see ops/sale/claims_verification_2026-09-25.md.

## Strengths
What a buyer might ask about | The strength (every line true under diligence) | Proof to show | Verified 2026-09-25 (Claude Code)
No revenue yet | Clean slate: no legacy customers, refunds or churn. The buyer sets monetization from day one - sponsored rounds, featured slots, card on-ramp partner fees. | Revenue-lever sheet | [HOLDS] Framing, not a factual claim.
23 players, 3 votes to date | The buyer is paying for a proven machine at below replacement cost and bringing the audience - so every future vote is theirs. The numbers are stated plainly, which makes every other claim credible. | Replacement-cost sheet; round history | [HOLDS (one phrase pending)] Numbers verified against production 2026-09-25. "Below replacement cost" depends on outputs/sale/data_room/replacement_cost.md — quote its figure rather than the adjective.
Chainlink automation stalled in the past | Self-healing settlement, proven: Rounds 9-12 each settled unattended within 30 minutes of close - four in a row, verifiable onchain. | Basescan settlement txs, Rounds 9-12 | [HOLDS — tighter than claimed] Verified: settlement ran 19.6, 22.4, 17.3 and 18.3 minutes after close for rounds 9-12. PROVE IT FROM CHAIN (round_history.csv), never from admin_audit_log — three of the four SETTLE rows are wrongly recorded no_state_change, which makes the autopilot look worse than it is.
Token contract can't be upgraded | Immutable token: nobody - not us, not the buyer - can change its code. What diligence verifies is what runs forever, and any audit the buyer commissions stays valid permanently. | Empty EIP-1967 slot; bytecode on Basescan | [HOLDS] proxiableUUID() returns instead of reverting; EIP-1967 slot zero; 20,747B of code. Both token and V3d show "Contract Source Code Verified" on BaseScan.
Supply can be expanded | Supply is governed by a 2-of-2 multisig: expansion needs both signatures, so the owner can fund future rewards without a token migration. A 48-hour timelock package is ready to install at close if the buyer wants one. | Role map; timelock package (from Sep 28) | [HOLDS] Executed on a mainnet fork: granted MINTER, minted 1B, supply 69B to 70B. Timelock package is built and fork-tested but NOT executed.
Blacklist concerns from scanners | No blacklist - provably: the contract has no function that can ever freeze an address. | Source: blacklisted mapping has no setter | [NEEDS CAVEAT] Blacklist half VERIFIED — the mapping has no setter, no address can ever be blacklisted. But pause() exists; PAUSER_ROLE has no holders today (verified) and the Safe could grant it, freezing ALL transfers. Say it first: an auditor will. ADD: "A global pause exists; PAUSER_ROLE has no holders and the multisig would have to grant it — the 48h timelock makes that public and delayed."
Zero-value transfers revert | Disclosed up front with its scope: only a transfer of exactly zero tokens is affected. Normal transfers, swaps and the new liquidity route all passed fork tests. | Fork transcript; /audit table | [HOLDS] Scope confirmed on fork: only exactly-zero transfers revert. A 100 TTS taxed transfer delivered 99 TTS correctly.
Old audit claims were wrong | Full audit history disclosed, each finding mapped to the deployed code, and every public claim re-verified against chain and corrected. | /audit status table; original report | [HOLDS once the mapping table ships] The finding-to-bytecode table is being built and will be published on /audit.
Thin liquidity / Blockaid 'spam' label | Deeper liquidity with zero cash outlay: card buys up to $1,000 at 3.26% impact ($500 at 1.92%) once Safe tx #1 executes, funded with 0.0101% of the Safe's TTS. The no-blacklist finding backs the scanner appeal. | Fork measurements; Blockaid update | [HOLDS — add a condition] Fork-measured. Say "once Safe tx #1 executes" every single time; it is not true yet.
Placeholder profiles | [STRUCK 2026-09-25] AI Models division: always-on demo content plus a clearly labeled AI category - the category Fanvue built its growth on with the Miss AI pageant. | Board screenshots; rotation log | [STRUCK] Not built. Zero AI profiles exist, no badge or filter ships in any client, and ops/sale/rotation_log.csv does not exist. Blocked on IMAGE_API_KEY. USE INSTEAD: "Schema and constraints for a labelled AI-model category are deployed; generation and display are not built yet." Do not offer board screenshots or a rotation log as proof.
No iOS App Store listing | [STRUCK 2026-09-25] iPhone users are served through the web app and Telegram - no Apple review gate and no 30% commission. The TestFlight build transfers for a buyer who wants a native route. | PWA install guide; TestFlight build | [STRUCK] "TestFlight build transfers" is false — mobile/eas.json still holds three REPLACE_WITH_* placeholders and there is no Apple Developer account, so no TestFlight build exists. The PWA install guide does not exist either. USE INSTEAD: "The iOS project is configured for TestFlight and needs only an Apple Developer account." The no-review-gate / no-30%-commission points do hold.
Main X account locked | Telegram-first community with a native bot, plus the automated Social Composer ready for any handle the buyer runs. | Composer logs; Telegram stats | [UNVERIFIED] Could not verify X account state or Telegram community size from here. Do not cite "Telegram stats" or "Composer logs" as proof without pulling the actual numbers.
Founder is part-time | [STRUCK 2026-09-25] Runs on automation: settlement autopilot, Social Composer, daily digest, weekly AI rotation. Documented for AI-assisted maintenance (CLAUDE.md). | Ops runbook; cost sheet | [STRUCK IN PART] "Weekly AI rotation" does not exist. The daily digest is built and scheduled but has never sent (no Proton Bridge credentials). USE INSTEAD: "Runs on automation: settlement autopilot (proven over four consecutive rounds), Social Composer, and a daily operations digest."
Adult-adjacent | Brand-safe SFW public face with a direct channel into the creator-agency market - fits mainstream marketplaces and adult-industry strategic buyers alike. | Site + agency pipeline | [HOLDS with care] SFW public face is true and now enforced. The "agency pipeline" is a built outreach engine that has never sent — do not imply active relationships.
Legal questions | [STRUCK 2026-09-25] Legal review complete; free signup tokens and a free first vote built in. | Counsel sign-off letter | [STRUCK] No counsel sign-off letter exists — outputs/legal/ is all self-drafted (risk memo, terms, privacy, DMCA, trademark). "Free first vote" is not a feature. USE INSTEAD: "Policies drafted in-house plus a written risk memo; no external counsel opinion yet. New players get 500 $TTS free on signup — 100 minimum votes — so nobody has to buy in to play."
Token has no market price | Priced on the engine and distribution, not a chart - the buyer's price doesn't move with the market. | One-pager asset list | [NEEDS CAVEAT] There IS a thin market price via the Uniswap v2 pool. Say "no meaningful market price" or drop it. Never state the figure.
Google Play requires a closed test | [STRUCK 2026-09-25] Native Android distribution in progress: APK live now, Play listing through Google's quality gate. | Play Console status | [STRUCK] "APK live now" is false. No .apk exists in the repo or any route; app.temptationtoken.io/download returns the SPA catch-all shell, not a download. No Play Console app exists. USE INSTEAD: "Android build is code-complete and builds via EAS; no APK published yet."
The mechanic is copyable | Time-to-market: build, deployment, apps, entity and distribution groundwork are done - the replacement-cost sheet shows what a buyer skips. | Replacement-cost sheet | [HOLDS once the sheet ships] Depends on outputs/sale/data_room/replacement_cost.md.

## Platforms
Venue | What it is | Role in this sale | Seller cost | Timing | Site | Status
Acquire.Fi | Web3 M&A marketplace for crypto-native businesses | Primary venue | Seller form; selective acceptance | Submit Oct 1 | acquire.fi | Not started
SideProjectors | Free listing, no commission, no escrow | Secondary - fast | Free / 0% | Submit Oct 1 | sideprojectors.com | Not started
IndieMaker | Accepts pre-revenue | Secondary | 3% on pre-revenue (per July 2026 comparison) | Submit Oct 1 | indiemaker.co | Not started
ExitBid | 5-day auction format | Optional - price discovery | $199 flat, 0% (their own comparison - verify) | Optional | exitbid.io | Not started
Flippa | Largest general marketplace | Only with SFW engine framing + agency pilot disclosed, after Flippa confirms eligibility | $49-$499 listing + 5-10% | Ask support first | flippa.com | Not started
Acquire.com | Curated startup marketplace | After first revenue (pre-revenue only for SaaS/AI) | Monthly listing fee + closing commission | Later | acquire.com | Not started
Microns | Profitable micro-startups | Skip (pre-revenue declined) | 6-10% success fee | Skip | microns.io | Not started
Direct outreach | Acquirers tab - the real buyers | Primary | 0% | Oct 1 launch | - | Not started
r/SideProject, r/SaaSforSale | Communities | Check each sub's rules | Free | Oct 1 if allowed | reddit.com | Not started
Base ecosystem | base.dev registration + builder channels | Visibility with Web3 builders | Free | Sep 29 | base.dev | Not started
Notes: Flippa's rules exclude adult businesses including OnlyFans-supporting ones and bar selling accounts on other platforms — use it only if Flippa confirms eligibility for the SFW engine framing with the agency pilot disclosed. Acquire.com accepts pre-revenue listings only for functional SaaS/AI products. Fee figures for IndieMaker/ExitBid/SideProjectors/Flippa come from a July 2026 comparison written by ExitBid — verify on each site.

## Store Plan
Channel | Plan | Timing | Why it's a strength
Android - APK | Live now: direct download link on the homepage | Done / keep | Buyers can install it today
Android - Google Play | Personal account: 14-day closed test with 12+ testers, then apply for production. Organization account: submit now. Listing copy: 'vote for your favorites, win trophies' - declare tokenized assets, no earnings hype. | Start Sep 25 | Live around mid-October if the test starts Sep 25
iPhone - web app (PWA) | Add-to-Home-Screen install guide on the site; full app experience with no store gate | Sep 26 site rebuild | No Apple review, no 30% fee
iPhone - Telegram Mini App | @TemptationTokenBot opens app.temptationtoken.io inside Telegram | Existing path | Crypto-native users stay in Telegram
iOS - App Store | No submission: Apple's guideline 1.2 names 'hot-or-not' voting on real people as not belonging on the App Store. The TestFlight build transfers with the sale for a buyer who wants to pursue a native route. | Not submitting | Keeps the listing asset clean of a rejection record

## Audit & Liquidity
Audit readiness — verified findings on the deployed contracts and how each is disclosed or answered
Contract | Expected finding | Typical category | Mitigation before submission
Token | Governed supply: the Safe can grant itself MINTER_ROLE (proved on a fork: 69B -> 70B) | Centralization - can't be changed (immutable) | Disclosed; 2-of-2 multisig; 48h timelock package ready for the buyer at close
Token | transfer(x, 0) reverts with an arithmetic panic; the recorded M-1 fix never deployed | Low/Medium - can't be changed (immutable) | Disclosed with scope; normal transfers and swaps pass; a buyer can migrate to a v2 token if wanted
Token | Not a proxy - the token is immutable (earlier copy said UUPS) | Informational | App copy corrected; WordPress copy fixed by T66
Token | Blacklist mapping has no setter | Positive finding | Evidence for the Blockaid / GoPlus update (T73)
Token | 1% transfer tax + tax-exemption control | Owner privilege | Disclosed; exempt pools listed
Original SolidProof report | 1 critical + 3 high | Map each to the deployed code | T69 - fixed / not applicable / live; gate before card go-live
TTSVotingV3d | Privileged settlement fallback used by the keeper autopilot | Centralization / informational | Scoped role; settlement log published
TTSVotingV3d | Chainlink VRF subscription must stay funded | Informational | Auto-funder with reserve floor; LINK recovery (T70)
Staking proxy | Upgradeable (a real proxy - reverts correctly) | Centralization | Multisig; timelock option at close
Trophy NFT | Minter role | Low / informational | Held by the voting contract only; document
Audit budget reference (2026 market)
Simple token / NFT | $1,000-$10,000 · 2-8 days
Staking / governance / NFT systems | $5,000-$20,000 · 1-3 weeks
Rush turnaround | +20-50%
Source: QuillAudits, 'Smart Contract Audit Cost 2026' (market ranges). Sept 25 decision: no paid audit before an offer - the token is immutable, so a new report can only restate the two findings that can't change. Get a quote for negotiation; fund one only if a serious buyer makes it a closing condition.
Liquidity + card on-ramp plan (Safe tx #1 built and fork-verified; no cash outlay)
Step | Action | Who signs / runs | Gate
1 | Safe tx #1 (built + fork-verified): new concentrated pool, setTaxExempt(pool), single-sided position funded with 0.0101% of the Safe's 10B TTS | Jim + Mike sign (T10) | Expires Oct 9 - rebuild if price moves
2 | Measured result: max card buy ~$50 -> $1,000; $500 at 1.92% impact, $1,000 at 3.26% | Claude Code | Measured by actual swaps on a fork
3 | App routing: quote V2 + the new pool, route the better price; 5% impact guard stays | Claude Code | Deploy after tx #1 executes
4 | Map the original audit's critical/high findings to the deployed code | Claude Code (T69) | Gate before any card go-live
5 | Transak production key into Vercel; card tab on; $30 live test | Jim + Claude Code (T07, T20) | After steps 1 and 4
6 | Recover ~44 LINK: cancel + withdraw the retired upkeep; VRF to 25+ LINK first; remainder to ETH for sell-side depth | Claude Code builds (T70) | Gate met: Rounds 9-12 settled unattended
7 | Blockaid / GoPlus update with the no-blacklist evidence + new liquidity | Claude Code drafts, Jim sends (T73) | After tx #1 has run a few days

## Data Room
# | Item | Status | Location / link
1 | One-pager (asset list, what's live, real numbers, offer date) | Not started
2 | 2-3 minute Loom demo | Not started
3 | Contract list with Basescan links (token, TTSVotingV3d, staking proxy, Trophy NFT, Safe) | Not started
4 | Audit history: original SolidProof report + finding-status table vs. the deployed code + Slither/Aderyn pre-audit | Not started
5 | Replacement-cost sheet (what it would cost to build this, from git history) | Not started
6 | Round history export (every round: votes, winner, settlement tx, who settled) | Not started
7 | Metrics snapshot (players, votes, signups, card buys, pool depth) - real numbers only | Not started
8 | Architecture doc + CLAUDE.md operating manual | Not started
9 | Monthly running cost sheet (Vercel, Railway, Supabase, LINK, paymaster, hosting, email) | Not started
10 | Transfer runbook (Closing tab) + the ready-to-install timelock package | Not started
11 | Entity pack: Delaware certificate, EIN letter, operating agreement, member consent | Not started
12 | IP assignment (Jim to Blockchain Entertainment LLC) | Not started
13 | Counsel sign-off letter | Not started
14 | Strengths memo (Strengths tab, with the proof for each line) | Not started
15 | Store status (APK, Play, PWA, TestFlight) | Not started
16 | Site + SEO: Search Console / Bing data, indexed pages, AnswerPress content library | Not started
Member consent (Mike) — must say: (1) he consents to the sale of Blockchain Entertainment LLC's assets or of the LLC itself; (2) he will sign the Safe owner change and role transfers at close; (3) proceeds split per the operating agreement. Have the lawyer finalize.

## Closing
Asset | How it transfers | Where | Status
Safe | Add the buyer's signers, remove Jim's and Mike's (both sign) | Onchain | Not started
Contract roles | Move admin/upgrader to the buyer's Safe or timelock | Onchain | Not started
Optional timelock | Install the 48-hour timelock package if the buyer wants one | Onchain | Not started
Treasury + ecosystem tokens | Send to wallets the buyer generates | Onchain | Not started
LP positions | Transfer the position NFT / LP tokens (and any lock) to the buyer | Onchain | Not started
Chainlink VRF subscription | Request + accept subscription owner transfer | Onchain | Not started
Keeper autopilot / Bank wallet | Buyer deploys a new Bank key; move balances; revoke old | Onchain + Railway | Not started
Domains | temptationtoken.io (+ any others) push to buyer's registrar account | Registrar | Not started
WordPress + hosting | Hostinger account/site transfer; AnswerPress re-connection | Hosting | Not started
Code | GitHub repo transfer (incl. CLAUDE.md) | GitHub | Not started
Cloud | Vercel, Supabase, Railway project transfers | Each platform | Not started
Mobile | Expo/EAS project + Android keystore; Play app transfer; TestFlight build | Expo / Play | Not started
Telegram | BotFather > Transfer Ownership (2FA on 7+ days); channel/group ownership | Telegram | Not started
Payments | Transak (entity-bound if the LLC is sold; new KYB if assets only); CDP paymaster | Vendors | Not started
Email + scheduling | Proton custom-domain mailbox; Calendly | Vendors | Not started
Socials | LLC sale: accounts stay with the company. Asset sale: brand channels subject to each platform's rules - never priced as assets | Platforms | Not started
Secrets | Rotate every key and password after handover; buyer confirms | All | Not started
Exclude | Unsolicited airdrop tokens in the Bank wallet - never list, never interact | - | Not started
Wallet rule: move assets and roles onchain to wallets the buyer creates. Never hand over private keys or seed phrases — a buyer can never prove a handed-over key wasn't copied, and prices that risk in.

## Scoring Model
Predictive fit model — agency 'yes' likelihood (Sept 19, unchanged)
Score = weighted average of five 0-5 components, scaled to 100. P(meeting) comes from the band table. Both are starting assumptions (blue) — overwrite with your own reply data.
Component | Weight | What 5 means | What 0 means
Scale (roster size / reach) | 25% | 100+ creators or 400+ (Creators Inc); one yes = many weekly entrants | Solo operator / a handful of creators
Reachability of decision-maker | 25% | Named founder + published business email/Telegram | Anonymous team, intake form only
Openness (crypto / off-platform promo / performance marketing) | 20% | Multi-platform, Telegram-native, Dubai/EU, runs traffic ops | OnlyFans-only, discreet/no-face roster, no social promo
Reputation safety (inverse risk) | 15% | Clean press, registered company, transparent splits | Active litigation / creator-exploitation coverage
Meet-in-person access | 15% | Hosts or attends XBIZ/AVN/Swim Week/own events | No public events
Weight check (must be 100%)
P(meeting) bands — probability an agency books a call after the full sequence
Score floor | P(meeting) | Rationale
0 | 4% | Cold, hard-to-reach, low fit: email-only cold B2B response rates typically sit in low single digits
50 | 9% | Average fit with multi-channel follow-up (email + DM + phone)
65 | 15% | Good fit, reachable decision-maker
80 | 25% | Tier-1 fit + published direct channel or warm intro
Channel multipliers (assumptions — calibrate)
Touch / condition | Multiplier | Note
Warm intro (Rare X Network, Supercreator, a creator already on the board) | 2 | Referral beats cold in every outbound benchmark
Phone follow-up reached a human | 1.5 | Live conversation vs inbox
Met in person at an event | 3 | XBIZ/AVN/Swim Week hallway meeting
Email only, no other channel | 0.6 | Discount the band value if you skip DM + phone

## Targets
# | Agency | HQ / cities | Country | Time zone | Offset vs ET (hrs) | Person in charge (public) | Title | Verified public email | Website / apply / contact | Instagram | X / Telegram / other | Business phone (published) | Business mailing address (published) | Direct-contact route | Roster / scale signal (their claim unless noted) | Source URL(s) | Tier | Scale (0-5) | Reach (0-5) | Openness (0-5) | Rep safety (0-5) | Meet access (0-5) | Fit score | P(meeting) | Send 09:05 local = ET time | ET day | In Aug cohort-1? (Y/N) | Notes / risks / angle | Sale-track role (Sept 24)
1 | Creators Inc | Miami, FL (content house; events in Miami & NYC) | USA | America/New_York (EDT) | 0 | Andrew (Andy) Bachman | Founder & CEO | not published | creatorsinc.com/contact (form) · creatorsinc.com/apply | @creatorsinc | YouTube @creatorsinc · weekly podcast hosted by Bachman | not published | Not on site — pull principal address via FL Sunbiz | Founder is highly public (Entrepreneur, Inc., LA Weekly profiles; weekly podcast). Best route: pitch Bachman a podcast-guest/partnership angle via IG DM + LinkedIn; use Sunbiz address for direct mail. | ~700 employees, 400+ creators (Supercreator listing); $2B+ creator sales claim on site | https://www.creatorsinc.com/ · https://www.supercreator.app/agencies | 1 | 5 | 3 | 3 | 4 | 5 | [5 empty] | Largest roster found. Also the most natural strategic acquirer for TTS. Runs CI Swimwear show at Miami Swim Week = in-person window (late May/early June). | Acquirer track — see Acquirers tab
2 | AROA Agency | Miami, FL (HQ) · UK/ES/RO/UA/PT-BR sites | USA / UK | America/New_York (EDT) | 0 | not published | — | office@aroaagency.com (verified on site footer, Sept 2026) | aroaagency.com/uk/contact (form) | not published | Telegram t.me/aroaagency1 · YouTube @aroa_agency | not published | 8101 Biscayne Blvd, Ph 703-24, Miami, FL 33138 (site footer) | Email + Telegram published. Ask office@ for the founder/partnerships lead by name. Attends XBIZ/AVN (logos on site) = meet in person. | 30+ 'elite' creators, 150+ global team, 10+ yrs in adult industry; has a 'Refer Creators' program | https://aroaagency.com/uk | 1 | 3 | 5 | 4 | 4 | 5 | [5 empty] | Most reachable Tier-1. Referral culture = receptive to a weekly talent program. Multilingual (RO/UA/ES/PT) — could seed non-US creators. | Acquirer track — see Acquirers tab
3 | Louna's Models | Los Angeles (founded 2018) · Paris · Miami · Milan | USA / France | America/Los_Angeles (PDT) | -3 | Louna | Founder (former top creator) | not published | Supercreator listing → agency site (verify) | verify | Runs the 'Exclu Awards LA' creator event | not published | not published | Founder is the public face; approach via IG DM to Louna + event sponsorship/partnership ask. | 'Exclusive network of international talents'; female-only agency | https://www.supercreator.app/agencies | 1 | 3 | 4 | 4 | 4 | 5 | [5 empty] | Event owner = pitch a TTS award category / live vote at Exclu Awards. Four cities = multi-timezone roster. | Acquirer track — see Acquirers tab
4 | SheX Agency | Germany (DACH) | Germany | Europe/Berlin (CEST) | 6 | Named in Impressum (verify at she-x.de/impressum) | Geschäftsführer (per Impressum) | in Impressum (verify) | she-x.de | @onlyfans_agentur (13K) | Trustpilot 4.8 (132 reviews) | in Impressum (verify) | in Impressum (verify) | German law requires a named responsible person + email + address on the Impressum page — the cleanest direct contact in the whole list. | Claims 450+ staff and 'largest' management for OnlyFans, 4based, BestFans, Fancentro, Maloum (Trustpilot company blurb) | https://ca.trustpilot.com/review/she-x.de · https://www.instagram.com/onlyfans_agentur/ | 1 | 5 | 4 | 4 | 4 | 2 | [5 empty] | Multi-platform (not OF-only) → less TOS-sensitive to off-platform promo. Big DACH roster. Write in English; offer German landing copy. | Acquirer track — see Acquirers tab
5 | Rare X Network / Rare Agency | USA (verify city) | USA | America/New_York (verify) | 0 | not published | — | not published | rareagency.net | verify | — | not published | not published | Matching network that places creators with many agencies — one partnership = multi-agency reach. Approach as co-marketing partner, not as a single agency. | Network of partner agencies; free matching for creators (CreditDonkey review) | https://www.rareagency.net/ · https://www.creditdonkey.com/best-onlyfans-agency.html | 1 | 3 | 3 | 4 | 4 | 2 | [5 empty] | Channel multiplier. Offer: TTS as a perk they hand every placed creator. | Weekly enlistment — demand evidence
6 | Supercreator (software + agency directory) | Israel (directory lists 31 countries) | Israel | Asia/Jerusalem | 7 | not published | Partnerships / community | not published | supercreator.app/agencies · consultation Calendly on site | — | Telegram t.me/supercreator_app · X @Supercreatorapp · podcast on Spotify | not published | not published | Not an agency — the tool 25,000 creators/agencies use. Pitch: partner listing, podcast slot, co-marketing to their agency base. | 25,000 customers claim; directory of verified agencies | https://www.supercreator.app/agencies | 1 | 5 | 4 | 4 | 4 | 2 | [5 empty] | Highest-leverage single relationship: their directory IS the global list. | Acquirer track — see Acquirers tab
7 | Lost Boys Agency | verify (invite-only) | verify | verify | 0 | not published | — | not published | Instagram only | @lostboys.agency | — | not published | not published | Invite-only; IG DM or warm intro only. Do not cold email. | Claims $2M+/mo net sales; one talent $55M in debut year (their own PR) | https://www.instagram.com/lostboys.agency/ · https://secretsofonlyfans.gumroad.com | 1 | 5 | 1 | 3 | 3 | 2 | [5 empty] | Whale roster; low reachability. Worth one IG DM + one warm-intro attempt, then park. | Weekly enlistment — demand evidence
8 | Unruly Agency | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | Tara 'Electra' Niknejad; co-founder Nicky Gathrite | CEO; Co-founder | not published | unrulyagency.com (verify) | verify | — | not published | Not on site — CA SoS bizfile | CEO is named in press; LinkedIn/IG DM. Diligence first (see notes). | 100+ models/influencers, 500M combined reach (2021 BusinessWire) | https://www.businesswire.com/news/home/20210914005352/en/ · https://www.rollingstone.com/culture/culture-news/onlyfans-creators-unruly-agency-nudity-lawsuit-1320185/ | 2 | 4 | 3 | 3 | 2 | 3 | [5 empty] | Multiple creator lawsuits 2021-24; 2026 press releases say all claims dismissed/dropped. Reputation check before any public co-marketing — your 'never be seen as malicious' rule. | Weekly enlistment — demand evidence
9 | Behave Agency | Los Angeles (founded 2020) | USA | America/Los_Angeles (PDT) | -3 | not published | — (Unruly-affiliated) | not published | verify | verify | — | not published | not published | Same diligence as Unruly; contact via Unruly leadership. | Smaller-influencer arm of Unruly (Daily Beast) | https://www.cbinsights.com/company/behave-agency | 3 | 3 | 2 | 3 | 2 | 2 | [5 empty] | Named in the same suits as Unruly. | Weekly enlistment — demand evidence
10 | Sakura Management | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site (verify) | verify | — | not published | not published | Ex-webcam traffic firm → performance-marketing mindset; pitch the funnel math. | 5+ yrs; adult + mainstream creators (Supercreator listing, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 4 | 4 | 3 | [5 empty] | Traffic-ops DNA = understands CAC/LTV pitch. | Weekly enlistment — demand evidence
11 | Doris Agency / Doris Talent | Los Angeles · Miami | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site (verify) | verify | — | not published | not published | Site contact + IG DM. | Production company + influencer marketing (Supercreator, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 3 | 4 | 3 | [5 empty] | Brand-partnership oriented — frame TTS as a sponsor-ready property. | Weekly enlistment — demand evidence
12 | Seiren | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | verify | verify | — | not published | not published | Site form + IG. | Claims 'most of the top 1% creators' (Vocal Media roundup) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 4 | 2 | 3 | 4 | 3 | [5 empty] | Safety/comfort-first positioning — lead with consent agreement + no-OF-posting. | Weekly enlistment — demand evidence
13 | Teasy Agency | USA (verify city) | USA | verify (assume ET) | 0 | Co-founded by a female creator (name not published) | Co-founder | not published | teasyagency.com | verify | — | not published | not published | Site form; ask for co-founder by role. | Creator-founded; multi-tier management (site) | https://teasyagency.com/ | 2 | 3 | 3 | 3 | 4 | 2 | [5 empty] | Creator-led leadership responds to creator-benefit framing (trophies, weekly spotlight). | Weekly enlistment — demand evidence
14 | Think Expansion | Miami, FL | USA | America/New_York (EDT) | 0 | not published | — | not published | verify | verify | — | not published | not published | Site form. | 'One of the first OF agencies'; no-face/discreet models (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 2 | 4 | 3 | [5 empty] | Discreet roster = lower fit for a public photo leaderboard. Offer masked/creative-profile option or deprioritize. | Weekly enlistment — demand evidence
15 | Emerald Agency | Gold Coast, AU · Los Angeles | Australia / USA | Australia/Brisbane (AEST, no DST) | 14 | not published | — | not published | verify | verify | — | not published | not published | Site form; NYT Magazine feature gives a PR-savvy hook. | NYT Magazine-featured; exclusive roster (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 3 | 4 | 3 | [5 empty] | Dual timezone: send AU batch and LA batch separately. | Weekly enlistment — demand evidence
16 | Aruna Talent | verify country | verify | verify | 0 | not published | — | not published | arunatalent.com (apply) | verify | — | not published | not published | Site apply page + LinkedIn search 'Aruna Talent'. | 60+ creators, ~100-person team, $10M+/yr creator revenue (their own 'State of OnlyFans 2026' post) | https://arunatalent.com/blog/state-of-onlyfans-2026/ | 2 | 4 | 3 | 3 | 4 | 2 | [5 empty] | Publishes industry data — data-driven; send the EV calculator. | Weekly enlistment — demand evidence
17 | TDM Agency | verify (worldwide) | verify | verify | 0 | not published | — | not published | tdmmanagement.com | verify | — | not published | not published | Site form; Supercreator-verified listing. | 'World's leading' claim (Supercreator listing) | https://tdmmanagement.com/ · https://www.supercreator.app/agencies | 2 | 4 | 3 | 3 | 4 | 3 | [5 empty] | Cross-creator collab culture = weekly contest fits their playbook. | Weekly enlistment — demand evidence
18 | FansHub | UK & USA chat teams | UK / USA | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; Companies House for UK Ltd officers. | 20+ promo methods incl. meme pages, podcasts, influencer collabs (Talented Ladies Club) | https://www.talentedladiesclub.com/articles/five-best-onlyfans-management-agencies-in-2026/ | 2 | 3 | 3 | 4 | 4 | 2 | [5 empty] | Marketing-native — TTS is one more promo method for their stack. | Weekly enlistment — demand evidence
19 | Lush Management | UK HQ; roster US/UK/AU | UK | Europe/London (BST) | 5 | not published | — | not published | lushmgmt.co.uk/apply (form) | @thelushmgmt | X @lush_mgmt | not published | not published | Form + X/IG DM; Companies House for directors. | 'Nearly three years' experience; performance-only fees (site) | https://www.lushmgmt.co.uk/ | 2 | 3 | 3 | 3 | 4 | 2 | [5 empty] | Publishes Twitter/Reddit promo guides — comfortable with off-platform promo. | Weekly enlistment — demand evidence
20 | Rize Agency | UK | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; Companies House. | Claims $5k→$180k/mo client growth (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
21 | Elite OnlyFans Management | Australia · UK · Dubai | AU / UK / UAE | Asia/Dubai (GST) | 8 | not published | — | not published | eliteonlyfansmgmt.com (apply) | verify | — | not published | not published | Site form. | International team; ex-top-0.1% creators (site) | https://www.eliteonlyfansmgmt.com/ | 2 | 3 | 3 | 4 | 4 | 3 | [5 empty] | Dubai presence = crypto-comfortable. | Weekly enlistment — demand evidence
22 | Bunny Studios (Bunny Agency) | Germany (est. 2019) | Germany | Europe/Berlin (CEST) | 6 | Named in Impressum (verify) | Geschäftsführer | in Impressum (verify) | bunny-studios.com | @onlybunnyagency | — | in Impressum | in Impressum | Impressum. Confirm whether the Supercreator 'Bunny agency' listing is the same entity. | 'Top one OF agency in Europe' claim; no lock-in contracts (site) | https://bunny-studios.com/ · https://www.supercreator.app/agencies | 2 | 3 | 4 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
23 | NEO Agency | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | in Impressum | in Impressum | Impressum. | AI-driven growth positioning (Vocal Media) | https://vocal.media/filthy/top-10-best-only-fans-agencies-2024 | 2 | 3 | 4 | 4 | 4 | 2 | [5 empty] | Tech-forward — onchain trophies/gasless wallets are a feature. | Weekly enlistment — demand evidence
24 | NorthCoast Agency | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | in Impressum | in Impressum | Impressum. | '$6M+ earned for creators' claim (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 4 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
25 | Dolce Vita Agency | USA & Germany teams | USA / Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | not published | not published | Impressum (if DE entity) or site form. | 25+ creators, most top 0.02% (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 3 | 4 | 2 | [5 empty] | 'No PPV spam' ethos — lead with fan-experience framing. | Weekly enlistment — demand evidence
26 | Foxy Studios | EU (verify country; euro-denominated) | verify | Europe/Berlin (assume CEST) | 6 | not published | Female-led leadership team | not published | Supercreator listing → site | verify | — | not published | not published | Site/Impressum. | 55/45 split in creator's favor; real-time dashboards (Supercreator, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 3 | 4 | 2 | [5 empty] | Transparency brand — show the onchain audit page and prize split. | Weekly enlistment — demand evidence
27 | Magic Agency | verify (hosts meetups in USA, Thailand, Dubai, Europe, Brazil) | verify | verify | 6 | not published | — | not published | verify | verify | — | not published | not published | Site form; ask to attend a meetup. | Global creator meetups; weekly QA reports (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 4 | 4 | 4 | [5 empty] | Meetup culture = in-person pitch to founder + creators at once. | Weekly enlistment — demand evidence
28 | Upbrand | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | Tony Izzet | Founder | not published | Instagram | @upbrand.au (121K) · founder @tonyizzet | — | not published | not published | Founder is public on IG — DM him directly. ABN Lookup for the entity. | 'Scaling models globally to $40,000+/mo'; 'all spots currently filled' (IG bio) | https://www.instagram.com/upbrand.au/ | 2 | 3 | 4 | 3 | 4 | 2 | [5 empty] | 'Spots filled' = capacity-constrained; TTS adds revenue without adding headcount. | Acquirer track — see Acquirers tab
29 | Azzur Agency (OnlyFansManagement.com.au) | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | Leadership roles on About page (names: verify) | not published | onlyfansmanagement.com.au/about-us | verify | — | not published | not published | About page lists roles; ABN Lookup. | Talent/celebrities/public figures focus (site) | https://onlyfansmanagement.com.au/ | 2 | 3 | 3 | 3 | 4 | 2 | [5 empty] | Celebrity roster = bigger vote pull per creator. | Weekly enlistment — demand evidence
30 | SirenCY | verify (CY?) | verify | Europe/Nicosia (assume EEST) | 7 | not published | — | not published | sirency.com | verify | — | not published | not published | Site; treat their numbers as marketing until verified. | Claims 312+ creators, $50M+ managed (own blog) | https://www.sirency.com/blog/biggest-onlyfans-agencies-2026-the-major-players-revealed | 2 | 4 | 3 | 3 | 3 | 2 | [5 empty] | Verify before relying on scale. | Weekly enlistment — demand evidence
31 | Melossom Management | UK | UK | Europe/London (BST) | 5 | not published | — | not published | melossommgmt.com | verify | — | not published | not published | Site form; Companies House. | 'UK's leading' claim (site) | https://www.melossommgmt.com/ | 3 | 2 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
32 | Red Fox | UK | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form. | Custom packages; copywriters/analysts (AROA UK roundup) | https://aroaagency.com/uk/blog/the-biggest-best-onlyfans-agencies | 3 | 2 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
33 | Everlasting Eros / EROS Agency | London | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; confirm whether EROS Agency is the same firm. | Brand-strategy-first positioning | https://www.laxir.us/single-post/top-5-best-onlyfans-agencies-management-services | 3 | 2 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
34 | 20MG (Twenty Management Group) | USA-registered; serves US/UK/AU/CA | USA | America/New_York (assume EDT) | 0 | not published | — | not published | 20mg.co (apply) | verify | — | not published | not published | Site form. | Small deliberate roster; six-figure marketing budgets claim (site) | https://20mg.co/ | 3 | 2 | 3 | 3 | 4 | 2 | [5 empty] | Serves Canada — CASL: no cold email to Canadian contacts; use form/DM. | Weekly enlistment — demand evidence
35 | Xcelerate Agency | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | AI + social-media-marketing positioning (Supercreator, verified) | https://www.supercreator.app/agencies | 3 | 2 | 3 | 4 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
36 | 2TWENTYTWO | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Boutique, premium chatting (Supercreator, verified) | https://www.supercreator.app/agencies | 3 | 2 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
37 | WE ARE VERIFIED | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Talent-first management (Supercreator listing) | https://www.supercreator.app/agencies | 3 | 2 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
38 | Verge Agency | verify | verify | verify | 0 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Models, influencers, celebrities (Supercreator listing) | https://www.supercreator.app/agencies | 3 | 3 | 2 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
39 | OFM (of-management.com) | Nuremberg, Germany | Germany | Europe/Berlin (CEST) | 6 | Two brothers (names in Impressum — verify) | Founders | in Impressum (verify) | of-management.com | verify | — | in Impressum | in Impressum | Impressum. | Ex-B2B social agency turned OFM (site) | https://www.of-management.com/ | 3 | 2 | 4 | 3 | 4 | 2 | [5 empty] | B2B-marketing roots — will read an EV model. | Weekly enlistment — demand evidence
40 | Adler Agency | Germany (DACH, since 2024) | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | adleragency.de | verify | — | in Impressum | in Impressum | Impressum. | Selected models and agencies in DACH + worldwide (site) | https://www.adleragency.de/en | 3 | 2 | 4 | 3 | 4 | 2 | [5 empty] | Works with other agencies — possible sub-network. | Weekly enlistment — demand evidence
41 | FameGrowth | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | famegrowth.de | verify | — | in Impressum | in Impressum | Impressum. | 8+ yrs experience claim (site) | https://famegrowth.de/en | 3 | 2 | 4 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
42 | MAHO Management | DACH | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | maho-management.com | verify | — | in Impressum | in Impressum | Impressum. | Brand management + Instagram/TikTok/Twitch promo (site) | https://maho-management.com/en/ | 3 | 2 | 4 | 4 | 4 | 2 | [5 empty] | Twitch/streamer crossover — gaming-literate roster. | Weekly enlistment — demand evidence
43 | FEM Management | DACH | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | fem-management.com | verify | — | in Impressum | in Impressum | Impressum. | 24/7 DE/EN chat teams; leak protection (site) | https://www.fem-management.com/ | 3 | 2 | 4 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
44 | Die OnlyFans Agentur | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | die-onlyfans-agentur.de | verify | — | in Impressum | in Impressum | Impressum. | — | https://www.die-onlyfans-agentur.de/ | 3 | 2 | 4 | 3 | 3 | 2 | [6 empty] | Weekly enlistment — demand evidence
45 | Prosper Talent Management | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | prospermanagement.com.au | verify | — | not published | not published | Site form; ABN Lookup. | Performance-driven; hiring chat/ops staff (site) | https://www.prospermanagement.com.au/ | 3 | 2 | 3 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
46 | Flair Management | Sydney | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | flair-management.com | verify | — | not published | not published | Site form. | — | https://flair-management.com/ | 3 | 2 | 3 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
47 | Nest Talent Pty Ltd | Brisbane | Australia | Australia/Brisbane (AEST, no DST) | 14 | not published | — | not published | nesttalent.com | verify | — | not published | not published | Site form; ASIC/ABN for Pty Ltd officers. | Registered company; performance-based offer (site) | https://www.nesttalent.com/ | 3 | 2 | 3 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
48 | Aura Management | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | auramgmt.com.au | verify | — | not published | not published | Site form. | Traditional talent-management ethos; also non-female creators (site) | https://www.auramgmt.com.au/ | 3 | 2 | 3 | 3 | 4 | 2 | [6 empty] | Weekly enlistment — demand evidence
49 | OFM Models (ofmmodels.com) | verify (Telegram-first) | verify | verify | 6 | not published | — | not published | ofmmodels.com | verify | Telegram @ofmm_agency | not published | not published | Telegram DM. | Serves Japanese creators too; Telegram intake (site) | https://ofmmodels.com/en/blog/kto-sozdal-onlyfans | 3 | 2 | 4 | 4 | 3 | 1 | [5 empty] | Telegram-native — TTS bot integration is a natural fit. | Weekly enlistment — demand evidence
50 | Bop House (creator collective — not an agency) | Miami, FL | USA | America/New_York (EDT) | 0 | Managed collective | — | not published | via their management / Creators Inc relationship | verify | — | not published | not published | Reach through Creators Inc — not directly. | Highest-profile OF creator house (Wikipedia) | https://en.wikipedia.org/wiki/Bop_House · https://www.creatorsinc.com/ | 2 | 5 | 1 | 2 | 3 | 3 | [5 empty] | Warm intro only. | Weekly enlistment — demand evidence
51 | LONG TAIL — Supercreator directory (31 countries, paginated) | Serbia, Estonia, Slovenia, DR, Israel, Italy, UAE, Turkey, NL, Poland, Brazil, Canada, France, Ukraine, Sweden, Czechia, Bali, Argentina, India, Switzerland, Colombia, Bulgaria, Belgium, Costa Rica, Mexico, Spain… | Global | varies | 0 | — | — | — | https://www.supercreator.app/agencies (filter by country/city) | — | — | — | — | Work page by page; each listing links to the agency site → Impressum/contact/footer. | Directory of listed agencies (some verified by Supercreator) | https://www.supercreator.app/agencies | 3 | 3 | 3 | 3 | 3 | 2 | [5 empty] | Batch 10-15 new rows per week from here; keep the same scoring. | Weekly enlistment — demand evidence
Expected meetings from this list (sum of P(meeting), full multi-channel sequence)
Tier-1 / Tier-2 / Tier-3 count
Component scores (cols S-W) are analyst estimates from public info. Offsets: UK/EU clocks fall back Oct 25, US Nov 1, Sydney springs forward Oct 4 — recheck send times after those dates.

## Events & Hangouts
Where buyers and agency owners are — business venues only
Event / venue | City | Dates | Who you'll meet | The play | Status | Source
XBIZ Show / XBIZ Week (+ X3 Expo, XMAs) | Los Angeles | Jan 7-10, 2027 | Agency execs, platform reps, performers, marketers; AROA exhibits/attends | Book business-lounge meetings from the target list; demo the weekly vote on a tablet | Dates confirmed on xbizshow.com (Sept 19 check) | https://www.xbizshow.com/
AVN Adult Entertainment Expo + AVN Awards | Las Vegas | Late Jan 2027 (confirm) | Largest consumer+trade adult expo; agencies scout talent | Booth-side weekly-vote demo | Confirm on avn.com | https://avn.com/
Rick's Cabaret New York (RCI Hospitality) | NYC - 50 W 33rd St | Any evening (call ahead) | Venue GM; RCI has hosted investor meet-ups here | 60-second /clubs demo + ask for a corporate intro | Business venue | RCI earnings call transcript
NJ clubs on your /clubs list | New Jersey | Oct 8 evening (Plan tab) | Owners/GMs | Sign up 2-3 clubs on the spot = demand evidence | Your list | -
Miami Swim Week — CI Swimwear (Creators Inc) | Miami | Late May / early June (confirm) | Andy Bachman + roster | Gifting-suite slot = time with the #1 target's founder | Confirm | https://www.creatorsinc.com/
Exclu Awards LA (Louna's Models) | Los Angeles | Confirm with Louna's | Top creators + Louna | Propose a TTS-powered fan-vote award | Confirm | https://www.supercreator.app/agencies
Exxxotica Expo | Edison NJ · Chicago · DC · Miami | Confirm 2026-27 dates | Creators, fans, some agency managers | Creator signup drive on home turf | Confirm | https://en.wikipedia.org/wiki/Exxxotica_Expo
Creators Inc podcast | Online | Weekly | Andy Bachman | Pitch yourself as a guest (pro-sports S&C coach + Prime documentary + creator economy) | Open | https://www.creatorsinc.com/
Supercreator Telegram + podcast | Online | Ongoing | Agency owners | Partner listing / guest slot | Open | https://www.supercreator.app/agencies
LinkedIn | Online | Daily | Founders/CEOs on the Acquirers tab | Connect note, then Email 2 content as a message | Open | -

## Agency EV Calculator
What TTS is worth to an agency — plug their numbers in on the call (inputs blue/yellow; outputs are formulas)
Frame: TTS is a zero-labor top-of-funnel. Each creator on the weekly board gets a profile that routes voters to her link hub. Token prizes are upside — enter 0 unless you have the verified figure.
INPUTS
Weekly active voters on the board (YOUR live number — replace) | 1000 | Pull from admin; example value only
Creators on the board in a typical round | 30 | Example value
Share of voters who view a given creator's profile | 20% | Assumption — measure in-app
Profile → link-hub click-through | 10% | Assumption — add UTM to each hub link and measure
Link-hub → paid subscription conversion | 3% | Assumption; agencies know their own number — ask
Average subscription price ($/mo) | 10 | Agency input
Platform fee (OnlyFans keeps 20%) | 20% | OnlyFans standard split
Agency share of creator NET revenue | 40% | Industry range roughly 20-50% — agency input
Average months a new sub stays | 2.5 | Agency input
Agency labor per creator per week (hours) to participate | 0.25 | Uploading a photo + posting the vote link
Agency labor cost ($/hour) | 20 | Agency input
Creators the agency enters per week | 10 | The ask
Expected token/prize value per creator per week ($) — VERIFIED figure only, else 0 | 0 | Leave 0 until the prize split is confirmed; never promise a pool size
Fans each entered creator brings in as voters per week | 50 | Assumption — the network effect: every roster brings its own voters
Share of those fans who sign up through the agency's referral link | 30% | Assumption
Referral payout per referred signup (TTS) — VERIFIED figure only, else 0 | 0 | Verify in admin before quoting
TTS price used for valuation ($) — pool-realizable price, else 0 | 0 | Only value what the pool can absorb
OUTPUTS (per creator per week unless stated)
Effective weekly voters (base + fans the entered creators bring)
Profile views per creator per week
Link-hub clicks per creator per week
New paid subs per creator per week
Creator gross from those subs over their lifetime ($)
Creator net after platform fee ($)
Agency revenue from those subs ($)
Agency labor cost per creator per week ($)
Agency net per creator per week, subs only ($)
Agency referral revenue per creator per week ($)
Agency net per creator per week incl. referral + verified prize share ($)
Agency weekly net for the creators entered ($)
Agency annualized net ($) — 52 rounds
Break-even link-hub→sub conversion (labor covered, subs only)
Return on labor (net ÷ labor cost)
How to use on a call: ask for THEIR sub price, agency share and hub→sub conversion, leave the TTS-side assumptions as-is, and read rows 35-36 back to them. If row 37 (break-even conversion) is below their real conversion, participation pays at zero prize value.