## READ ME
Temptation Token — Sell This Software Plan v2 (Sept 25, 2026)
Built on the Sept 19 agency workbook. Every Sept 19 tab is kept (Targets, Scoring Model, Events, EV Calculator); the sale-plan tabs are new. Sender identity for all TTS correspondence: jim@temptationtoken.io.
DASHBOARD
Offer review date | 2026-10-16
Days until offer review | 21
Plan tasks | 75
Plan tasks marked Done | 0
Plan completion | 0%
Acquirers on the list | 13
Acquirers with a meeting booked or later | 0
Agencies on the Sept 19 target list | 51
HOW THE AUTOMATION WORKS
1. Plan tab = the master schedule (ET). The same tasks are in TTS_Sale_Plan_Proton.ics (import into Proton Calendar) and tasks.json (feeds the 7:00 AM daily email).
2. Daily email: tts_daily_digest.py runs on your Mac every morning at 7:00 AM ET through Proton Mail Bridge and sends today's tasks + tomorrow's preview + live numbers.
3. Status column (Plan, Acquirers): pick from the dropdown. The dashboard above counts it.
4. Owners: Jim = only you can do it. Jim + Mike = both signatures. Claude Code = runs on your Mac from the sprint prompt. Auto = scheduled, nothing to do.
LEGEND
Blue text = inputs you can change. Black = formulas or fixed text. Yellow fill = verify or fill in. Orange rows on Plan = launch day and offer day.
CONTACT RULES (kept from Sept 19)
Only business contacts from public sources are listed. 'Not published' means no public source was found — the Other routes column gives the legitimate way in (forms, LinkedIn, Impressum, Companies House, state registries). No personal numbers or home addresses, by design.
Canada (ManyVids): no cold email under CASL — LinkedIn or phone only. UK/EU: B2B email with a clear identity and opt-out. US: CAN-SPAM footer with the LLC postal address.
WHAT CHANGED IN V2 (SEPT 25)
Corrected against the overnight onchain verification: the token is immutable (not a proxy), supply is governed by the 2-of-2 Safe, no blacklist is possible, the timelock is a closing-day option rather than executed, and there is no paid audit before an offer. New tasks T66-T75 (WordPress fixes, Bridge password, footer address, audit-finding map, LINK recovery, replacement-cost sheet, traction push, scanner update, walk-away price). Email 1 and the Strengths, Audit & Liquidity, Data Room and Closing tabs were rewritten to match.
WHAT CHANGED SINCE SEPT 19
New tabs: Plan, Acquirers, Sequence, Scripts, Strengths, Platforms, Store Plan, Audit & Liquidity, Data Room, Closing. The old Send Schedule tab is replaced by Plan (sale mode). The Targets tab keeps all agencies for weekly enlistment — every enrolled agency is demand evidence for the sale.

## Plan
ID | Date | Day | Time (ET) | Owner | Workstream | Task | How / detail | Status | Done on | Notes
T01 | 2026-09-24 | Thu | 20:00 | Jim | OPS | Turn on Telegram two-step verification | On the Telegram account that owns @TemptationTokenBot and the channels: Settings > Privacy & Security > Two-Step Verification. Starts the 7-day clock Telegram requires before a bot can change owners. Do not change the password afterward. | Not started
T02 | 2026-09-24 | Thu | 20:15 | Jim | LEGAL | Send Mike the member consent + Safe-signer agreement | Written consent to sell (assets or the LLC) plus his agreement to sign the Safe transfer at close. Checklist: Data Room tab. | Not started
T03 | 2026-09-24 | Thu | 21:00 | Jim | OPS | Paste the Claude Code sprint prompt and let it run overnight | File: TTS_Sale_Sprint_ClaudeCode.md. Opens the site to crawlers, generates the AI Models batch, fork-tests the liquidity move, runs the pre-audit, installs the daily reminder email. | Not started
T04 | 2026-09-25 | Fri | 07:00 | Auto | OPS | First daily digest email arrives | Starts once the Bridge password is in .env (T67). Then every day at 7:00 AM ET through Nov 6. | Not started
T66 | 2026-09-25 | Fri | 07:30 | Jim | SITE | Fix the 7 false claims on WordPress - '45% APR' first | Replacement text: outputs/site/false_claims_2026-09-25.md. Edit each page by hand in WP admin / Elementor (revision-safe). If a page takes more than 5 minutes, set it to Draft until it's fixed. | Not started
T67 | 2026-09-25 | Fri | 08:00 | Jim | OPS | Put the Proton Bridge password into .env | Bridge app > your account > copy the Bridge password (not your Proton login) into Claude Code's masked prompt. Unblocks the daily email, the canary and all outreach. | Not started
T68 | 2026-09-25 | Fri | 08:15 | Jim | LEGAL | Choose the postal address for TTS email footers | CAN-SPAM needs a valid postal address. A USPS P.O. box or a virtual mailbox for Blockchain Entertainment LLC keeps your home and other businesses off TTS mail. Give it to Claude Code. | Not started
T05 | 2026-09-25 | Fri | 08:30 | Jim | STORE | Check Google Play account type | Play Console > Settings > Developer account > Account details. Personal (created after Nov 13, 2023) = 14-day closed test with 12+ testers first. Organization = submit to production now. Tell Claude Code which. | Not started
T06 | 2026-09-25 | Fri | 09:00 | Jim | AUDIT | Optional: SolidProof quote request (quote only - no money before an offer) | The draft with disclosures is in outputs/sale/. A quote gives you a 'cost to certify' number for negotiation; fund an audit only if a serious buyer asks for one as a closing condition. | Not started
T07 | 2026-09-25 | Fri | 09:30 | Jim | LIQ | Transak: generate the PRODUCTION API key | Business verification is done, so pull the production key in the Transak dashboard and hand it to Claude Code through its secure prompt (never paste keys in chat). | Not started
T08 | 2026-09-25 | Fri | 10:00 | Jim | AI | Create an image-generation API key | Replicate, fal.ai or OpenAI. Add IMAGE_API_KEY to the repo .env. Costs pennies per image. | Not started
T69 | 2026-09-25 | Fri | 11:00 | Claude Code | AUDIT | Map the original audit's 1 critical + 3 high to the deployed code | Each one: fixed / not applicable / live. Anything live and exploitable = no card go-live until it's mitigated. Results go on /audit. | Not started
T09 | 2026-09-25 | Fri | 12:00 | Jim | LIQ | Read the liquidity fork-test report | outputs/sale/liquidity_forktest.md: card-buy sizes before/after, price impact, and exactly what Safe transaction #1 does. | Not started
T10 | 2026-09-25 | Fri | 13:00 | Jim + Mike | LIQ | Sign Safe transaction #1: liquidity | Built and fork-verified: new pool, tax exemption, single-sided position funded with 0.0101% of the Safe's TTS - no ETH, no cash. Max card buy goes from ~$50 to $1,000 ($500 at 1.92% impact, $1,000 at 3.26%). Expires Oct 9 - rebuild if the price moves. | Not started
T70 | 2026-09-25 | Fri | 14:00 | Claude Code | LIQ | Recover the ~44 LINK - autopilot gate met | Rounds 9-12 settled unattended. Build the cancel/withdraw transaction(s); top the VRF subscription to 25+ LINK first; remainder to ETH for sell-side depth. | Not started
T11 | 2026-09-25 | Fri | 15:00 | Jim | AI | Approve the AI Models batch in admin | Approval queue in admin. Reject anything that looks under 25, any nudity, any resemblance to a real person. | Not started
T12 | 2026-09-25 | Fri | 16:00 | Jim | STORE | Personal Play account only: recruit 15-20 testers | Send the closed-test opt-in link from outputs/listings/play_closed_test.md. 12 must stay opted in 14 straight days; over-recruit so attrition never resets the clock. | Not started
T13 | 2026-09-25 | Fri | 17:00 | Jim | SITE | Verify temptationtoken.io in Google Search Console + Bing Webmaster | DNS TXT record at the registrar, then import the site into Bing Webmaster Tools. Unlocks the traffic data buyers ask for. | Not started
T14 | 2026-09-26 | Sat | 10:00 | Claude Code | SITE | WordPress plugin v1.2 + robots.txt check | Authenticated write routes for posts, pages and options so Claude Code can maintain the site. Also print temptationtoken.io/robots.txt as served and remove any AI-crawler Disallow lines. | Not started
T71 | 2026-09-26 | Sat | 11:00 | Claude Code | DATA | Replacement-cost sheet for the data room | What it would cost a buyer to build this - components, hours at market rates, calendar time - from git history. Backs the asking price. | Not started
T15 | 2026-09-26 | Sat | 14:00 | Jim | SITE | Upload plugin v1.2 in WP admin (Plugins > Add New > Upload) | Two minutes. Unlocks API edits to the site from then on. | Not started
T16 | 2026-09-27 | Sun | 11:00 | Jim | DATA | Record the 2-3 minute Loom demo | Board > Face ID signup > vote > trophy on Basescan > admin > club signup > AI Models division. Paste the link into LOOM_URL. | Not started
T17 | 2026-09-27 | Sun | 18:00 | Jim | DATA | Review the data room draft | outputs/sale/data_room/ - mark anything to add. | Not started
T18 | 2026-09-28 | Mon | 07:00 | Auto | AI | AI Models rotation #1 | Runs after the round settles. Retires the oldest AI entries, activates the next approved batch; one extra retires for each new verified creator. | Not started
T19 | 2026-09-28 | Mon | 09:00 | Claude Code | AUDIT | Build + fork-test the 48-hour timelock package - do NOT execute | Parked as a closing-day option for the buyer. Handing admin to a timelock on an immutable token can't be undone, so it happens only if the buyer wants it. | Not started
T20 | 2026-09-28 | Mon | 10:00 | Jim | LIQ | Live card test: buy $30 of TTS by card on your phone | Only after T69 finds no live critical/high issue and Safe tx #1 has executed. Confirms Transak > swap > wallet end to end in production. | Not started
T21 | 2026-09-28 | Mon | 11:00 | Claude Code | SITE | IndexNow push + request indexing on the top 10 pages | Every URL goes to IndexNow engines within hours; Google via Search Console. | Not started
T72 | 2026-09-28 | Mon | 12:00 | Jim | OUTREACH | Traction push: post each round to your Telegram and X | Every real vote raises the price. Share the round link, the free first vote and the 500 TTS signup bonus. Real people only - buyers check onchain. | Not started
T22 | 2026-09-28 | Mon | 14:00 | Jim | STORE | Play: org account > submit production; personal > confirm 12+ testers opted in | Listing copy: outputs/listings/play_store_listing.md. | Not started
T23 | 2026-09-29 | Tue | 10:00 | Jim | OUTREACH | Register TTS on base.dev and submit the mini app form | Builder presence in the Base ecosystem; your paymaster already meets the sponsored-gas criterion. | Not started
T24 | 2026-09-29 | Tue | 11:00 | Jim | DATA | Approve the one-pager and listing drafts | outputs/sale/listings/ (Acquire.Fi, SideProjectors, IndieMaker). | Not started
T73 | 2026-09-29 | Tue | 11:00 | Claude Code | LIQ | Draft the Blockaid / GoPlus update for Jim to send | Evidence: the contract has no blacklist setter, plus the deeper liquidity from Safe tx #1. | Not started
T25 | 2026-09-29 | Tue | 14:00 | Jim | OUTREACH | LinkedIn: follow every decision-maker on the Acquirers tab | Warms up the Oct 1 connection requests. | Not started
T74 | 2026-09-29 | Tue | 16:00 | Jim + Mike | CLOSE | Agree your private walk-away price | Anchors stay $95K structured / $65K all-cash. The floor stays between you two and off every document. | Not started
T26 | 2026-09-30 | Wed | 10:00 | Jim | LEGAL | Put counsel's sign-off letter in the data room | Send counsel a short note first that the old site claims were found and corrected (with dates) so the letter reflects the current site. One page confirming the review is complete. | Not started
T27 | 2026-09-30 | Wed | 11:00 | Claude Code | SITE | Final QA: crawler test per bot, speed, schema, links | Report: outputs/site/qa_final.md. | Not started
T28 | 2026-09-30 | Wed | 16:00 | Jim | OUTREACH | Approve the Oct 1 automated batch | Claude Code queues each email for 9:05 AM recipient-local time; a canary copy to you fires first. | Not started
T29 | 2026-10-01 | Thu | 09:05 | Auto | OUTREACH | LAUNCH - Email 1 to AROA + RCI investor relations | office@aroaagency.com; gfishman@pondel.com + mwichman@pondel.com. SheX goes at 3:05 AM ET (9:05 Berlin) once the Impressum address is verified. | Not started
T30 | 2026-10-01 | Thu | 09:30 | Jim | OUTREACH | Submit listings: Acquire.Fi, SideProjectors, IndieMaker | Same one-pager everywhere. Offers reviewed Fri Oct 16. | Not started
T31 | 2026-10-01 | Thu | 10:00 | Jim | OUTREACH | Contact forms: Creators Inc, Fanvue, Infloww, The Clueless | Paste Email 1 with each company's hook (Scripts tab). | Not started
T32 | 2026-10-01 | Thu | 10:30 | Jim | OUTREACH | LinkedIn connection requests with note | Monange, Fitzgerald, Morris (Fanvue); Bachman (Creators Inc); Langan (RCI); Cruz (The Clueless); Etelis (Fansly); French (ManyVids); Bouslama (Acquire.Fi). | Not started
T33 | 2026-10-01 | Thu | 12:30 | Jim | OUTREACH | DMs: Instagram, Telegram, X | IG: @creatorsinc / Andy Bachman, @tonyizzet, Louna. Telegram: t.me/supercreator_app. X: @Acquire_Fi. | Not started
T34 | 2026-10-02 | Fri | 10:00 | Jim | OUTREACH | Reply to every response within an hour; book calls | calendly.com/temptationtoken/phone-meeting. Screen-share the live app, not slides. | Not started
T35 | 2026-10-02 | Fri | 12:30 | Jim | OUTREACH | Telegram follow-up to AROA | t.me/aroaagency1 - one line + the Loom. | Not started
T75 | 2026-10-03 | Sat | 10:00 | Claude Code | SITE | Optional: site rebuild on staging (same look) | Only after every public claim is true. Buyers forgive a dated layout, not a false claim. | Not started
T36 | 2026-10-05 | Mon | 07:00 | Auto | AI | AI Models rotation #2 | Automatic after settlement. | Not started
T37 | 2026-10-05 | Mon | 10:00 | Jim | OUTREACH | Weekly results note to engaged buyers | Round winner, votes, new creators, pool depth, card buys. Claude Code drafts it from live data. | Not started
T38 | 2026-10-06 | Tue | 09:05 | Auto | OUTREACH | Email 2 (proof + data room under NDA) to AROA + RCI IR | Includes the Loom and what shipped since Oct 1. | Not started
T39 | 2026-10-06 | Tue | 10:00 | Jim | OUTREACH | Email 2 via LinkedIn messages and forms | Same content to every accepted connection and form contact. | Not started
T40 | 2026-10-07 | Wed | 10:30 | Jim | OUTREACH | Call RCI investor relations: 212-883-0655 | Ask who evaluates digital partnerships or acquisitions; send a same-day recap email. Script: Scripts tab. | Not started
T41 | 2026-10-07 | Wed | 11:30 | Jim | OUTREACH | One-line follow-up DMs to non-responders | Line + Loom link. | Not started
T42 | 2026-10-08 | Thu | 18:00 | Jim | OUTREACH | Visit 2-3 clubs from your club list with the /clubs QR | Goal: signed-up clubs = demand evidence for the data room. Optional: Rick's Cabaret New York, 50 W 33rd St - ask for the GM and a corporate intro. | Not started
T43 | 2026-10-09 | Fri | 09:00 | Jim | STORE | Personal Play account: closed test hits 14 days - apply for production | Answers: outputs/listings/play_production_answers.md. | Not started
T44 | 2026-10-09 | Fri | 12:00 | Jim | AUDIT | Check SolidProof status; answer any questions same day |  | Not started
T45 | 2026-10-12 | Mon | 07:00 | Auto | AI | AI Models rotation #3 | Automatic after settlement. | Not started
T46 | 2026-10-12 | Mon | 09:05 | Auto | OUTREACH | Email 3 ('offers reviewed Friday') to AROA + RCI IR | Jim sends the same note via LinkedIn/forms at 10:00. | Not started
T47 | 2026-10-13 | Tue | 10:00 | Jim | DATA | Open the data room to every buyer who signed the NDA | Track who opened what - interest signal. | Not started
T48 | 2026-10-14 | Wed | 12:00 | Claude Code | AUDIT | Refresh the /audit status table (every finding vs. the deployed code) | Replaces the 'publish a new audit' step - no pre-sale audit purchase. | Not started
T49 | 2026-10-15 | Thu | 17:00 | Jim | OUTREACH | Last-call note to engaged buyers | 'Reviewing offers tomorrow at 5 PM ET.' | Not started
T50 | 2026-10-16 | Fri | 17:00 | Jim + Mike | CLOSE | OFFERS REVIEW | Rank by total value, cash at close, earn-out terms, certainty, speed. Best structure beats biggest headline. | Not started
T51 | 2026-10-19 | Mon | 07:00 | Auto | AI | AI Models rotation #4 | Automatic after settlement. | Not started
T52 | 2026-10-19 | Mon | 10:00 | Jim | CLOSE | Counter/accept, sign the LOI, engage the lawyer | Asset purchase vs. LLC purchase per CPA advice. | Not started
T53 | 2026-10-21 | Wed | 10:00 | Jim | CLOSE | Open escrow; buyer deposit |  | Not started
T54 | 2026-10-23 | Fri | 10:00 | Jim | CLOSE | Buyer diligence Q&A session | Data room + live walkthrough. | Not started
T55 | 2026-10-25 | Sun | 09:00 | Jim | OPS | Clock change: UK/EU fell back - London is ET+4 until Nov 1 |  | Not started
T56 | 2026-10-26 | Mon | 07:00 | Auto | AI | AI Models rotation #5 | Automatic after settlement. | Not started
T57 | 2026-10-26 | Mon | 10:00 | Claude Code | CLOSE | Transfer rehearsal on a fork | Safe owner swap, role moves, bot transfer checklist, project transfers - dry run. | Not started
T58 | 2026-10-28 | Wed | 10:00 | Jim + Mike | CLOSE | Sign the purchase agreement |  | Not started
T59 | 2026-11-01 | Sun | 09:00 | Jim | OPS | Clock change: US fell back - all times now EST |  | Not started
T60 | 2026-11-02 | Mon | 07:00 | Auto | AI | AI Models rotation #6 (skip if closed) |  | Not started
T61 | 2026-11-02 | Mon | 10:00 | Jim | CLOSE | Escrow funded - start transfers per the runbook | Closing tab, in order. | Not started
T62 | 2026-11-03 | Tue | 10:00 | Jim + Mike | CLOSE | Transfers day 1: Safe owner swap + roles + treasury to buyer wallets | Onchain moves only - never hand over keys or seed phrases. | Not started
T63 | 2026-11-04 | Wed | 10:00 | Jim | CLOSE | Transfers day 2: domains, hosting, repo, cloud projects, Expo/Play, Telegram bot |  | Not started
T64 | 2026-11-05 | Thu | 10:00 | Claude Code | CLOSE | Rotate every key and secret; verify buyer controls everything |  | Not started
T65 | 2026-11-06 | Fri | 12:00 | Jim | CLOSE | Buyer confirms receipt - escrow releases funds | Sale closed. | Not started

## Acquirers
ID | Tier | Company | Category | HQ / time zone | Decision-maker(s) (public) | Title | Verified business contact (published) | Other routes | Visit / in person | Why they buy (strength framing) | Opening hook | Structure to lead with | Outreach law | Source(s) | Verified? | Status | Next step | Next date
A1 | 1 | Fanvue | Fan platform - AI-creator category leader | London (Canary Wharf) - ET+5 until Oct 25, then ET+4 until Nov 1 | Will Monange; Harry Fitzgerald; Joel Morris | Co-founder & CEO; Co-founder & COO; Co-founder | Business email not published in the sources checked | LinkedIn (all three founders); fanvue.com business contact; public developer API (integration angle) | London HQ by appointment; XBIZ LA Jan 7-10, 2027 | Built its growth on AI creators and runs the Miss AI pageant - TTS is a weekly onchain fan vote with a disclosed AI Models division next to verified creators, ready to plug into Fanvue's public API. | Miss AI proved fans will vote on AI creators. We run that vote every week, onchain, with an AI Models division beside verified creators. | Cash + earn-out tied to creators onboarded; or tech acquisition + 60-day consulting | UK PECR B2B: identify yourself, give an opt-out | BusinessWire Jan 12 2026 (Series A, founders' titles); Las Vegas Sun Jul 10 2026 ($200M run rate, CEO); Wikipedia/Fanvue (AI creators, Miss AI, public API 2025) | Names/titles: yes. Email/phone: not published | Not contacted
A2 | 1 | Creators Inc | OnlyFans management agency - largest roster found | Miami, FL - ET | Andrew (Andy) Bachman | Founder & CEO | Not published (site uses a contact form) | creatorsinc.com/contact form; Instagram @creatorsinc; weekly podcast (guest pitch); FL Sunbiz for the principal address (direct mail) | Miami Swim Week - CI Swimwear show (late May/early June) | 400+ creators. Owning the vote means owning a weekly traffic event for the entire roster instead of renting attention. | Your roster is the biggest audience in the category. The platform that turns it into a weekly event is built and running. | Cash + earn-out; or equity partnership | US CAN-SPAM | Sept 19 workbook (creatorsinc.com; Supercreator directory) | Name/title: yes. Email: not published | Not contacted
A3 | 1 | AROA Agency | OnlyFans management agency (multi-country) | Miami, FL (HQ) - ET | Not published - ask office@ for the partnerships lead by name | - | office@aroaagency.com (site footer, verified Sept 2026); 8101 Biscayne Blvd, Ph 703-24, Miami, FL 33138 | Telegram t.me/aroaagency1; aroaagency.com/uk/contact | XBIZ / AVN (attends) | Refer-Creators program = referral economics; TTS pays referral rewards onchain every week across a multilingual roster. | Your Refer-Creators program already runs on referral economics - this runs it onchain, weekly, for every creator you place. | Cash + earn-out | US CAN-SPAM | aroaagency.com/uk (Sept 19 verification) | Email + address: yes | Not contacted
A4 | 1 | Infloww | Agency software (OnlyFans CRM) moving into AI + fintech | London - ET+5 until Oct 25 | Not published - UK Companies House lists the directors | Director(s) | Not published | infloww.com contact; Companies House officer search; LinkedIn | - | Diversifying into AI tools and fintech - TTS is a finished fan-engagement + payments layer its agency customers can switch on. | You're building into AI and fintech. Here's a finished engagement-and-payments layer your agencies could turn on next month. | Cash acquisition of the engine + optional revenue share | UK PECR B2B | Company profile (London private limited, founded 2019, ~45 staff); WebCatalog (AI + fintech diversification) | Company facts: yes. Decision-maker: look up | Not contacted
A5 | 1 | Supercreator (supercreator.app) | Agency software + global agency directory | Tel Aviv - ET+7 | Co-founders Yuval and Amir (surnames not published in sources found) | Co-founders | Not published | Telegram t.me/supercreator_app; X @Supercreatorapp; consultation Calendly on supercreator.app | - | Their directory is the global agency list - TTS becomes a perk they hand every listed agency, or a product they own outright. | Your directory is where agencies live. This is a weekly traffic engine you could hand every one of them. | Cash + rev share on agencies onboarded | B2B with opt-out | Startup registry profile (founded 2022, Tel Aviv); Sept 19 workbook (channels) | Channels: yes. Full names: no | Not contacted
A6 | 1 | RCI Hospitality Holdings (NASDAQ: RICK) | Public club operator (60+ locations) | Houston, TX - ET-1 | Eric Langan | Chairman, President & CEO | Media & investor contacts (published Nov 2025): Gary Fishman & Michael Wichman, 212-883-0655, gfishman@pondel.com, mwichman@pondel.com | X @RCIHHinc; LinkedIn (Langan) | Rick's Cabaret New York, 50 W 33rd St, NYC (business venue) | 60+ venues whose customers want to be seen; the /clubs flow lets any venue run its own weekly fan vote from a phone - fan engagement that drives door traffic. | Your venues already sell the experience of being seen. This lets every club run a weekly fan vote from a phone and send fans back through the door. | Cash; or license + pilot across 5 venues | US CAN-SPAM | BusinessWire Nov 14 2025 (contacts; Langan title); RCI release Jan 2023 (60+ locations) | IR contacts: yes | Not contacted
A7 | 2 | The Clueless | AI-model agency (creator of Aitana Lopez) | Barcelona - ET+6 | Ruben Cruz | Co-founder & Creative Director | Not published in sources checked | theclueless.ai contact; LinkedIn | - | Runs AI talent that already earns on Fanvue - an AI Models division needs exactly their roster, and owning the stage beats renting it. | Aitana showed AI talent can build a real audience. We built the weekly stage where fans vote for it. | Cash or equity swap | EU GDPR B2B legitimate interest | Wikipedia/Aitana Lopez; Reason.Why (Cruz title); press on Fanvue presence | Name/title: yes | Not contacted
A8 | 2 | Fansly | Fan platform (bootstrapped) | Baltimore, MD (Select Media LLC) / Cyprus (CY Media LTD) - ET | Michael Etelis | Founder / owner | Not published | Maryland business registry (Select Media LLC address) for direct mail; LinkedIn; fansly.com business contact | - | Competes on creator features - a weekly spotlight that sends fans to creators' pages is a feature they can ship next week. | Fansly grew by giving creators a better home. This gives them a weekly spotlight that sends fans straight to their page. | Cash acquisition | US CAN-SPAM | Wikipedia/Fansly; MEL Magazine (ownership) | Name: yes. Contact: not published | Not contacted
A9 | 2 | ManyVids | Creator platform | Montreal - ET | Bella French | Co-founder (CEO title per Wikipedia infobox; verify current title) | Not published | LinkedIn; corporate phone if published on their site | - | Creator-first brand - a weekly fan-vote contest is an engagement feature that fits their residuals story. | You built ManyVids around fair pay for creators. This adds a weekly fan vote that pays creators in attention. | Cash acquisition | Canada CASL - NO cold email. LinkedIn or phone only | Wikipedia/ManyVids | Name: yes | Not contacted
A10 | 1 | Acquire.Fi | Web3 M&A marketplace (venue + buyer network) | Remote / BVI | Nassim Bouslama; Jan Strandberg | Co-founder & CEO; Co-founder & CTO | Seller form on acquire.fi | X @Acquire_Fi; LinkedIn | - | Web3 buyers who want a working onchain product with apps, entity and distribution - not a whitepaper. | - | Listed ask: $95K structured / $65K all-cash | - | CoinDesk profile (founders); G2 (marketplace scope) | Names: yes | Not contacted
A11 | 2 | Louna's Models | Agency - runs the Exclu Awards | Los Angeles - ET-3 | Louna | Founder | Not published | Instagram DM | Exclu Awards LA | Owns an awards event - a TTS-powered fan-vote award category turns into ownership of the vote itself. | Exclu Awards is the closest thing to what we run every week - except our vote is onchain. | Cash + partnership | US CAN-SPAM | Sept 19 workbook | Name: yes | Not contacted
A12 | 2 | Upbrand | Agency (Australia) | Australia - ET+14 (ET+15 after Oct 4) | Tony Izzet | Founder | Not published | Instagram @tonyizzet | - | Capacity-constrained ('all spots filled') - a self-running engine adds revenue without headcount. | Your bio says every spot is filled. This adds revenue per creator without adding a single hire. | Cash + earn-out | Australia Spam Act | Sept 19 workbook (Instagram) | Name: yes | Not contacted
A13 | 2 | SheX Agency | Agency (DACH, multi-platform) | Germany - ET+6 | Named in the Impressum (verify at she-x.de/impressum) | Geschaeftsfuehrer | Impressum email (legally required - Claude Code verifies before sending) | Instagram @onlyfans_agentur | - | Runs creators across several platforms, so off-platform promotion is already their model. | You already run creators across five platforms - this is the one that brings fans to all of them. | Cash + earn-out | EU GDPR B2B | Sept 19 workbook (Trustpilot, Instagram) | Route: yes | Not contacted
Tier 1 count | 7
Tier 2 count | 6
Structure note: list the full package at $95K structured (cash + earn-out) or $65K all-cash. The gap nudges buyers toward structure. Never lead with token price. Your private floor stays off every document.

## Sequence
Acquirer ID | Company | Date | Day | Time (ET) | Channel | Action | Script (Scripts tab) | Status
A13 | SheX Agency | 2026-10-01 | Thu | 03:05 | Email (auto) | Email 1 to the verified Impressum address (9:05 Berlin) | Email 1 - acquirer | Not started
A3 | AROA Agency | 2026-10-01 | Thu | 09:05 | Email (auto) | Email 1 to office@aroaagency.com | Email 1 - acquirer | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-01 | Thu | 09:05 | Email (auto) | Email 1 to gfishman@pondel.com + mwichman@pondel.com | Email 1 - acquirer | Not started
A10 | Acquire.Fi | 2026-10-01 | Thu | 09:30 | Listing form | Submit the Acquire.Fi seller form |  | Not started
A1 | Fanvue | 2026-10-01 | Thu | 10:00 | Web form | Email 1 + Fanvue hook via fanvue.com business contact | Email 1 - acquirer | Not started
A2 | Creators Inc | 2026-10-01 | Thu | 10:00 | Web form | Email 1 via creatorsinc.com/contact | Email 1 - acquirer | Not started
A4 | Infloww | 2026-10-01 | Thu | 10:00 | Web form | Email 1 via infloww.com contact | Email 1 - acquirer | Not started
A7 | The Clueless | 2026-10-01 | Thu | 10:00 | Web form | Email 1 via theclueless.ai | Email 1 - acquirer | Not started
A1 | Fanvue | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Monange, Fitzgerald, Morris | LinkedIn connection note | Not started
A2 | Creators Inc | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Andy Bachman | LinkedIn connection note | Not started
A4 | Infloww | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to directors found on Companies House | LinkedIn connection note | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Eric Langan | LinkedIn connection note | Not started
A7 | The Clueless | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Ruben Cruz | LinkedIn connection note | Not started
A8 | Fansly | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Michael Etelis | LinkedIn connection note | Not started
A9 | ManyVids | 2026-10-01 | Thu | 10:30 | LinkedIn | Connect note to Bella French (no cold email - CASL) | LinkedIn connection note | Not started
A10 | Acquire.Fi | 2026-10-01 | Thu | 12:30 | X | DM @Acquire_Fi with the one-pager link | DM | Not started
A11 | Louna's Models | 2026-10-01 | Thu | 12:30 | Instagram | DM Louna - award-category + ownership angle | DM | Not started
A12 | Upbrand | 2026-10-01 | Thu | 12:30 | Instagram | DM @tonyizzet | DM | Not started
A2 | Creators Inc | 2026-10-01 | Thu | 12:30 | Instagram | DM @creatorsinc + Bachman (podcast-guest + acquisition angle) | DM | Not started
A5 | Supercreator (supercreator.app) | 2026-10-01 | Thu | 12:30 | Telegram | DM t.me/supercreator_app + book the consultation Calendly | DM | Not started
A8 | Fansly | 2026-10-02 | Fri | 10:00 | Web form | Email 1 via fansly.com business contact | Email 1 - acquirer | Not started
A3 | AROA Agency | 2026-10-02 | Fri | 12:30 | Telegram | Nudge on t.me/aroaagency1 + Loom |  | Not started
A13 | SheX Agency | 2026-10-06 | Tue | 03:05 | Email (auto) | Email 2 | Email 2 - proof | Not started
A3 | AROA Agency | 2026-10-06 | Tue | 09:05 | Email (auto) | Email 2 (proof + data room) | Email 2 - proof | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-06 | Tue | 09:05 | Email (auto) | Email 2 (proof + data room) | Email 2 - proof | Not started
A1 | Fanvue | 2026-10-06 | Tue | 10:00 | LinkedIn | Email 2 (proof + data room) to accepted connections | Email 2 - proof | Not started
A10 | Acquire.Fi | 2026-10-06 | Tue | 10:00 | Email / X | Follow-up with Loom + audit status |  | Not started
A2 | Creators Inc | 2026-10-06 | Tue | 10:00 | IG / LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A4 | Infloww | 2026-10-06 | Tue | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A5 | Supercreator (supercreator.app) | 2026-10-06 | Tue | 10:00 | Telegram | Email 2 content (proof + data room) | Email 2 - proof | Not started
A7 | The Clueless | 2026-10-06 | Tue | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A8 | Fansly | 2026-10-06 | Tue | 10:00 | LinkedIn | Email 2 (proof + data room) | Email 2 - proof | Not started
A9 | ManyVids | 2026-10-06 | Tue | 10:00 | LinkedIn | Email 2 content via message | Email 2 - proof | Not started
A11 | Louna's Models | 2026-10-06 | Tue | 12:30 | Instagram | Proof DM with Loom | DM | Not started
A12 | Upbrand | 2026-10-06 | Tue | 12:30 | Instagram | Proof DM with Loom | DM | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-07 | Wed | 10:30 | Phone | Call IR at 212-883-0655 - ask who evaluates digital deals | Call opener | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-08 | Thu | 18:00 | Visit (optional) | Rick's Cabaret New York - GM demo + corporate intro | Club visit | Not started
A13 | SheX Agency | 2026-10-12 | Mon | 03:05 | Email (auto) | Email 3 | Email 3 - offer date | Not started
A3 | AROA Agency | 2026-10-12 | Mon | 09:05 | Email (auto) | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A6 | RCI Hospitality Holdings (NASDAQ: RICK) | 2026-10-12 | Mon | 09:05 | Email (auto) | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A1 | Fanvue | 2026-10-12 | Mon | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A2 | Creators Inc | 2026-10-12 | Mon | 10:00 | IG / LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A4 | Infloww | 2026-10-12 | Mon | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A5 | Supercreator (supercreator.app) | 2026-10-12 | Mon | 10:00 | Telegram | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A7 | The Clueless | 2026-10-12 | Mon | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A8 | Fansly | 2026-10-12 | Mon | 10:00 | LinkedIn | Email 3 - offers reviewed Oct 16 | Email 3 - offer date | Not started
A9 | ManyVids | 2026-10-12 | Mon | 10:00 | LinkedIn | Offers reviewed Oct 16 |  | Not started
A1 | Fanvue | 2026-10-15 | Thu | 17:00 | LinkedIn | Last call (if engaged) | Call opener | Not started

## Scripts
Script | Text (fill {{FirstName}}, {{Company}}, {{Hook}} from the Acquirers tab)
Email 1 - acquirer (Oct 1) | Subject A: Acquisition: a working onchain fan-voting platform Subject B: {{Company}} + a weekly fan-vote engine you could own Hi {{FirstName}}, {{Hook}} I'm Jim Goetz, founder of Temptation Token. We built a complete weekly fan-voting platform on Base: fans vote for creators, winners receive onchain trophies, and every creator's profile sends voters straight to her link hub. Working today: - Web app, Android app, Telegram bot - Face ID sign-up with gas-free wallets; card purchases through Transak - Weekly rounds that settle themselves onchain - every vote and winner publicly verifiable - Club self-serve onboarding, referral engine, automated social posting - An AI Models division, clearly labeled, ready for agency creators to join - Contracts verified on Base: supply governed by a 2-of-2 multisig, no blacklist function, full audit history disclosed - Delaware entity, domains, brand, and an SEO site that publishes automatically My other companies need my full attention, so Temptation Token needs a full-time owner. We're reviewing offers on Friday, October 16. If owning it makes sense for {{Company}}, I'll open the data room under NDA - 20 minutes is enough to see it live: calendly.com/temptationtoken/phone-meeting Jim Goetz Founder, Temptation Token - Blockchain Entertainment LLC jim@temptationtoken.io
Email 2 - proof (Oct 6) | Subject: 2-minute walkthrough + data room - Temptation Token {{FirstName}} - here's the platform running live: [LOOM_URL] New since last week: [SHIPPED_THIS_WEEK - e.g. card purchases live, deeper liquidity, audit underway, Round # settled] The data room covers contracts, round history, metrics, architecture, monthly running cost, and the transfer runbook. Reply 'NDA' and I'll send it today. Offers are reviewed Friday, October 16. Jim
Email 3 - offer date (Oct 12) | Subject: Offers reviewed Friday - Temptation Token {{FirstName}} - a quick note that we're reviewing offers this Friday, October 16 at 5 PM ET. Cash, cash plus earn-out, and partnership structures are all on the table. If a 20-minute look would help before then: calendly.com/temptationtoken/phone-meeting Jim
LinkedIn connection note (300 chars max) | Jim Goetz, founder of Temptation Token - a working onchain fan-voting platform (web, Android, Telegram). We're reviewing acquisition offers Oct 16 and {{Company}} is a natural fit. Worth a 20-minute look?
DM - Instagram / X / Telegram | {{FirstName}} - Jim Goetz, founder of Temptation Token. We built a weekly onchain fan vote: creators get a spotlight, fans vote, winners get trophies, and every profile sends fans to the creator's page. We're selling it to an owner with a roster - {{Company}} fits. Can I send the 2-minute walkthrough?
Call opener - RCI investor relations (Oct 7) | Hi Gary, Jim Goetz, founder of Temptation Token. I emailed you and Michael last week. We're selling a turnkey fan-engagement platform with a self-serve club program - any venue can run its own weekly fan vote from a phone. Who at RCI looks at digital partnerships or acquisitions? I'd like to get them a 20-minute demo before we review offers on the 16th.
Voicemail (20 seconds) | Hi, it's Jim Goetz with Temptation Token - I sent a note about a weekly fan-vote platform we're selling to an owner with a roster or venues. The two-minute walkthrough is in your inbox; my email is jim@temptationtoken.io. We're reviewing offers October 16. Thanks.
Club visit (60 seconds) | Hi, I'm Jim Goetz with Temptation Token. We run a weekly fan vote for entertainers - your club can join from a phone in about two minutes, and it sends fans back through your door. Can I show you on my phone? [Scan the /clubs QR together.]
Placeholders | [LOOM_URL] = your demo link. [SHIPPED_THIS_WEEK] = Claude Code fills from live data. Claude Code verifies every line against chain and the live app before Oct 1 and strikes anything that doesn't hold. Never state a prize-pool dollar figure, token price, APR or return.

## Strengths
What a buyer might ask about | The strength (every line true under diligence) | Proof to show
No revenue yet | Clean slate: no legacy customers, refunds or churn. The buyer sets monetization from day one - sponsored rounds, featured slots, card on-ramp partner fees. | Revenue-lever sheet
23 players, 3 votes to date | The buyer is paying for a proven machine at below replacement cost and bringing the audience - so every future vote is theirs. The numbers are stated plainly, which makes every other claim credible. | Replacement-cost sheet; round history
Chainlink automation stalled in the past | Self-healing settlement, proven: Rounds 9-12 each settled unattended within 30 minutes of close - four in a row, verifiable onchain. | Basescan settlement txs, Rounds 9-12
Token contract can't be upgraded | Immutable token: nobody - not us, not the buyer - can change its code. What diligence verifies is what runs forever, and any audit the buyer commissions stays valid permanently. | Empty EIP-1967 slot; bytecode on Basescan
Supply can be expanded | Supply is governed by a 2-of-2 multisig: expansion needs both signatures, so the owner can fund future rewards without a token migration. A 48-hour timelock package is ready to install at close if the buyer wants one. | Role map; timelock package (from Sep 28)
Blacklist concerns from scanners | No blacklist - provably: the contract has no function that can ever freeze an address. | Source: blacklisted mapping has no setter
Zero-value transfers revert | Disclosed up front with its scope: only a transfer of exactly zero tokens is affected. Normal transfers, swaps and the new liquidity route all passed fork tests. | Fork transcript; /audit table
Old audit claims were wrong | Full audit history disclosed, each finding mapped to the deployed code, and every public claim re-verified against chain and corrected. | /audit status table; original report
Thin liquidity / Blockaid 'spam' label | Deeper liquidity with zero cash outlay: card buys up to $1,000 at 3.26% impact ($500 at 1.92%) once Safe tx #1 executes, funded with 0.0101% of the Safe's TTS. The no-blacklist finding backs the scanner appeal. | Fork measurements; Blockaid update
Placeholder profiles | AI Models division: always-on demo content plus a clearly labeled AI category - the category Fanvue built its growth on with the Miss AI pageant. | Board screenshots; rotation log
No iOS App Store listing | iPhone users are served through the web app and Telegram - no Apple review gate and no 30% commission. The TestFlight build transfers for a buyer who wants a native route. | PWA install guide; TestFlight build
Main X account locked | Telegram-first community with a native bot, plus the automated Social Composer ready for any handle the buyer runs. | Composer logs; Telegram stats
Founder is part-time | Runs on automation: settlement autopilot, Social Composer, daily digest, weekly AI rotation. Documented for AI-assisted maintenance (CLAUDE.md). | Ops runbook; cost sheet
Adult-adjacent | Brand-safe SFW public face with a direct channel into the creator-agency market - fits mainstream marketplaces and adult-industry strategic buyers alike. | Site + agency pipeline
Legal questions | Legal review complete; free signup tokens and a free first vote built in. | Counsel sign-off letter
Token has no market price | Priced on the engine and distribution, not a chart - the buyer's price doesn't move with the market. | One-pager asset list
Google Play requires a closed test | Native Android distribution in progress: APK live now, Play listing through Google's quality gate. | Play Console status
The mechanic is copyable | Time-to-market: build, deployment, apps, entity and distribution groundwork are done - the replacement-cost sheet shows what a buyer skips. | Replacement-cost sheet

## Platforms
Venue | What it is | Role in this sale | Seller cost | Timing | Site | Status
Acquire.Fi | Web3 M&A marketplace for crypto-native businesses | Primary venue | Seller form; selective acceptance | Submit Oct 1 | acquire.fi | Not started
SideProjectors | Free listing, no commission, no escrow | Secondary - fast | Free / 0% | Submit Oct 1 | sideprojectors.com | Not started
IndieMaker | Accepts pre-revenue | Secondary | 3% on pre-revenue (per July 2026 comparison) | Submit Oct 1 | indiemaker.co | Not started
ExitBid | 5-day auction format | Optional - price discovery | $199 flat, 0% (their own comparison - verify) | Optional | exitbid.io | Not started
Flippa | Largest general marketplace | Only with SFW engine framing + agency pilot disclosed, after Flippa confirms eligibility | $49-$499 listing + 5-10% | Ask support first | flippa.com | Not started
Acquire.com | Curated startup marketplace | After first revenue (pre-revenue only for SaaS/AI) | Monthly listing fee + closing commission | Later | acquire.com | Not started
Microns | Profitable micro-startups | Skip (pre-revenue declined) | 6-10% success fee | Skip | microns.io | Not started
Direct outreach | Acquirers tab - the real buyers | Primary | 0% | Oct 1 launch | - | Not started
r/SideProject, r/SaaSforSale | Communities | Check each sub's rules | Free | Oct 1 if allowed | reddit.com | Not started
Base ecosystem | base.dev registration + builder channels | Visibility with Web3 builders | Free | Sep 29 | base.dev | Not started
Notes: Flippa's rules exclude adult businesses including OnlyFans-supporting ones and bar selling accounts on other platforms — use it only if Flippa confirms eligibility for the SFW engine framing with the agency pilot disclosed. Acquire.com accepts pre-revenue listings only for functional SaaS/AI products. Fee figures for IndieMaker/ExitBid/SideProjectors/Flippa come from a July 2026 comparison written by ExitBid — verify on each site.

## Store Plan
Channel | Plan | Timing | Why it's a strength
Android - APK | Live now: direct download link on the homepage | Done / keep | Buyers can install it today
Android - Google Play | Personal account: 14-day closed test with 12+ testers, then apply for production. Organization account: submit now. Listing copy: 'vote for your favorites, win trophies' - declare tokenized assets, no earnings hype. | Start Sep 25 | Live around mid-October if the test starts Sep 25
iPhone - web app (PWA) | Add-to-Home-Screen install guide on the site; full app experience with no store gate | Sep 26 site rebuild | No Apple review, no 30% fee
iPhone - Telegram Mini App | @TemptationTokenBot opens app.temptationtoken.io inside Telegram | Existing path | Crypto-native users stay in Telegram
iOS - App Store | No submission: Apple's guideline 1.2 names 'hot-or-not' voting on real people as not belonging on the App Store. The TestFlight build transfers with the sale for a buyer who wants to pursue a native route. | Not submitting | Keeps the listing asset clean of a rejection record

## Audit & Liquidity
Audit readiness — verified findings on the deployed contracts and how each is disclosed or answered
Contract | Expected finding | Typical category | Mitigation before submission
Token | Governed supply: the Safe can grant itself MINTER_ROLE (proved on a fork: 69B -> 70B) | Centralization - can't be changed (immutable) | Disclosed; 2-of-2 multisig; 48h timelock package ready for the buyer at close
Token | transfer(x, 0) reverts with an arithmetic panic; the recorded M-1 fix never deployed | Low/Medium - can't be changed (immutable) | Disclosed with scope; normal transfers and swaps pass; a buyer can migrate to a v2 token if wanted
Token | Not a proxy - the token is immutable (earlier copy said UUPS) | Informational | App copy corrected; WordPress copy fixed by T66
Token | Blacklist mapping has no setter | Positive finding | Evidence for the Blockaid / GoPlus update (T73)
Token | 1% transfer tax + tax-exemption control | Owner privilege | Disclosed; exempt pools listed
Original SolidProof report | 1 critical + 3 high | Map each to the deployed code | T69 - fixed / not applicable / live; gate before card go-live
TTSVotingV3d | Privileged settlement fallback used by the keeper autopilot | Centralization / informational | Scoped role; settlement log published
TTSVotingV3d | Chainlink VRF subscription must stay funded | Informational | Auto-funder with reserve floor; LINK recovery (T70)
Staking proxy | Upgradeable (a real proxy - reverts correctly) | Centralization | Multisig; timelock option at close
Trophy NFT | Minter role | Low / informational | Held by the voting contract only; document
Audit budget reference (2026 market)
Simple token / NFT | $1,000-$10,000 · 2-8 days
Staking / governance / NFT systems | $5,000-$20,000 · 1-3 weeks
Rush turnaround | +20-50%
Source: QuillAudits, 'Smart Contract Audit Cost 2026' (market ranges). Sept 25 decision: no paid audit before an offer - the token is immutable, so a new report can only restate the two findings that can't change. Get a quote for negotiation; fund one only if a serious buyer makes it a closing condition.
Liquidity + card on-ramp plan (Safe tx #1 built and fork-verified; no cash outlay)
Step | Action | Who signs / runs | Gate
1 | Safe tx #1 (built + fork-verified): new concentrated pool, setTaxExempt(pool), single-sided position funded with 0.0101% of the Safe's 10B TTS | Jim + Mike sign (T10) | Expires Oct 9 - rebuild if price moves
2 | Measured result: max card buy ~$50 -> $1,000; $500 at 1.92% impact, $1,000 at 3.26% | Claude Code | Measured by actual swaps on a fork
3 | App routing: quote V2 + the new pool, route the better price; 5% impact guard stays | Claude Code | Deploy after tx #1 executes
4 | Map the original audit's critical/high findings to the deployed code | Claude Code (T69) | Gate before any card go-live
5 | Transak production key into Vercel; card tab on; $30 live test | Jim + Claude Code (T07, T20) | After steps 1 and 4
6 | Recover ~44 LINK: cancel + withdraw the retired upkeep; VRF to 25+ LINK first; remainder to ETH for sell-side depth | Claude Code builds (T70) | Gate met: Rounds 9-12 settled unattended
7 | Blockaid / GoPlus update with the no-blacklist evidence + new liquidity | Claude Code drafts, Jim sends (T73) | After tx #1 has run a few days

## Data Room
# | Item | Status | Location / link
1 | One-pager (asset list, what's live, real numbers, offer date) | Not started
2 | 2-3 minute Loom demo | Not started
3 | Contract list with Basescan links (token, TTSVotingV3d, staking proxy, Trophy NFT, Safe) | Not started
4 | Audit history: original SolidProof report + finding-status table vs. the deployed code + Slither/Aderyn pre-audit | Not started
5 | Replacement-cost sheet (what it would cost to build this, from git history) | Not started
6 | Round history export (every round: votes, winner, settlement tx, who settled) | Not started
7 | Metrics snapshot (players, votes, signups, card buys, pool depth) - real numbers only | Not started
8 | Architecture doc + CLAUDE.md operating manual | Not started
9 | Monthly running cost sheet (Vercel, Railway, Supabase, LINK, paymaster, hosting, email) | Not started
10 | Transfer runbook (Closing tab) + the ready-to-install timelock package | Not started
11 | Entity pack: Delaware certificate, EIN letter, operating agreement, member consent | Not started
12 | IP assignment (Jim to Blockchain Entertainment LLC) | Not started
13 | Counsel sign-off letter | Not started
14 | Strengths memo (Strengths tab, with the proof for each line) | Not started
15 | Store status (APK, Play, PWA, TestFlight) | Not started
16 | Site + SEO: Search Console / Bing data, indexed pages, AnswerPress content library | Not started
Member consent (Mike) — must say: (1) he consents to the sale of Blockchain Entertainment LLC's assets or of the LLC itself; (2) he will sign the Safe owner change and role transfers at close; (3) proceeds split per the operating agreement. Have the lawyer finalize.

## Closing
Asset | How it transfers | Where | Status
Safe | Add the buyer's signers, remove Jim's and Mike's (both sign) | Onchain | Not started
Contract roles | Move admin/upgrader to the buyer's Safe or timelock | Onchain | Not started
Optional timelock | Install the 48-hour timelock package if the buyer wants one | Onchain | Not started
Treasury + ecosystem tokens | Send to wallets the buyer generates | Onchain | Not started
LP positions | Transfer the position NFT / LP tokens (and any lock) to the buyer | Onchain | Not started
Chainlink VRF subscription | Request + accept subscription owner transfer | Onchain | Not started
Keeper autopilot / Bank wallet | Buyer deploys a new Bank key; move balances; revoke old | Onchain + Railway | Not started
Domains | temptationtoken.io (+ any others) push to buyer's registrar account | Registrar | Not started
WordPress + hosting | Hostinger account/site transfer; AnswerPress re-connection | Hosting | Not started
Code | GitHub repo transfer (incl. CLAUDE.md) | GitHub | Not started
Cloud | Vercel, Supabase, Railway project transfers | Each platform | Not started
Mobile | Expo/EAS project + Android keystore; Play app transfer; TestFlight build | Expo / Play | Not started
Telegram | BotFather > Transfer Ownership (2FA on 7+ days); channel/group ownership | Telegram | Not started
Payments | Transak (entity-bound if the LLC is sold; new KYB if assets only); CDP paymaster | Vendors | Not started
Email + scheduling | Proton custom-domain mailbox; Calendly | Vendors | Not started
Socials | LLC sale: accounts stay with the company. Asset sale: brand channels subject to each platform's rules - never priced as assets | Platforms | Not started
Secrets | Rotate every key and password after handover; buyer confirms | All | Not started
Exclude | Unsolicited airdrop tokens in the Bank wallet - never list, never interact | - | Not started
Wallet rule: move assets and roles onchain to wallets the buyer creates. Never hand over private keys or seed phrases — a buyer can never prove a handed-over key wasn't copied, and prices that risk in.

## Scoring Model
Predictive fit model — agency 'yes' likelihood (Sept 19, unchanged)
Score = weighted average of five 0-5 components, scaled to 100. P(meeting) comes from the band table. Both are starting assumptions (blue) — overwrite with your own reply data.
Component | Weight | What 5 means | What 0 means
Scale (roster size / reach) | 25% | 100+ creators or 400+ (Creators Inc); one yes = many weekly entrants | Solo operator / a handful of creators
Reachability of decision-maker | 25% | Named founder + published business email/Telegram | Anonymous team, intake form only
Openness (crypto / off-platform promo / performance marketing) | 20% | Multi-platform, Telegram-native, Dubai/EU, runs traffic ops | OnlyFans-only, discreet/no-face roster, no social promo
Reputation safety (inverse risk) | 15% | Clean press, registered company, transparent splits | Active litigation / creator-exploitation coverage
Meet-in-person access | 15% | Hosts or attends XBIZ/AVN/Swim Week/own events | No public events
Weight check (must be 100%) | 100%
P(meeting) bands — probability an agency books a call after the full sequence
Score floor | P(meeting) | Rationale
0 | 4% | Cold, hard-to-reach, low fit: email-only cold B2B response rates typically sit in low single digits
50 | 9% | Average fit with multi-channel follow-up (email + DM + phone)
65 | 15% | Good fit, reachable decision-maker
80 | 25% | Tier-1 fit + published direct channel or warm intro
Channel multipliers (assumptions — calibrate)
Touch / condition | Multiplier | Note
Warm intro (Rare X Network, Supercreator, a creator already on the board) | 2 | Referral beats cold in every outbound benchmark
Phone follow-up reached a human | 1.5 | Live conversation vs inbox
Met in person at an event | 3 | XBIZ/AVN/Swim Week hallway meeting
Email only, no other channel | 0.6 | Discount the band value if you skip DM + phone

## Targets
# | Agency | HQ / cities | Country | Time zone | Offset vs ET (hrs) | Person in charge (public) | Title | Verified public email | Website / apply / contact | Instagram | X / Telegram / other | Business phone (published) | Business mailing address (published) | Direct-contact route | Roster / scale signal (their claim unless noted) | Source URL(s) | Tier | Scale (0-5) | Reach (0-5) | Openness (0-5) | Rep safety (0-5) | Meet access (0-5) | Fit score | P(meeting) | Send 09:05 local = ET time | ET day | In Aug cohort-1? (Y/N) | Notes / risks / angle | Sale-track role (Sept 24)
1 | Creators Inc | Miami, FL (content house; events in Miami & NYC) | USA | America/New_York (EDT) | 0 | Andrew (Andy) Bachman | Founder & CEO | not published | creatorsinc.com/contact (form) · creatorsinc.com/apply | @creatorsinc | YouTube @creatorsinc · weekly podcast hosted by Bachman | not published | Not on site — pull principal address via FL Sunbiz | Founder is highly public (Entrepreneur, Inc., LA Weekly profiles; weekly podcast). Best route: pitch Bachman a podcast-guest/partnership angle via IG DM + LinkedIn; use Sunbiz address for direct mail. | ~700 employees, 400+ creators (Supercreator listing); $2B+ creator sales claim on site | https://www.creatorsinc.com/ · https://www.supercreator.app/agencies | 1 | 5 | 3 | 3 | 4 | 5 | 79 | 15% | 9:05 | same day |  | Largest roster found. Also the most natural strategic acquirer for TTS. Runs CI Swimwear show at Miami Swim Week = in-person window (late May/early June). | Acquirer track — see Acquirers tab
2 | AROA Agency | Miami, FL (HQ) · UK/ES/RO/UA/PT-BR sites | USA / UK | America/New_York (EDT) | 0 | not published | — | office@aroaagency.com (verified on site footer, Sept 2026) | aroaagency.com/uk/contact (form) | not published | Telegram t.me/aroaagency1 · YouTube @aroa_agency | not published | 8101 Biscayne Blvd, Ph 703-24, Miami, FL 33138 (site footer) | Email + Telegram published. Ask office@ for the founder/partnerships lead by name. Attends XBIZ/AVN (logos on site) = meet in person. | 30+ 'elite' creators, 150+ global team, 10+ yrs in adult industry; has a 'Refer Creators' program | https://aroaagency.com/uk | 1 | 3 | 5 | 4 | 4 | 5 | 83 | 25% | 9:05 | same day |  | Most reachable Tier-1. Referral culture = receptive to a weekly talent program. Multilingual (RO/UA/ES/PT) — could seed non-US creators. | Acquirer track — see Acquirers tab
3 | Louna's Models | Los Angeles (founded 2018) · Paris · Miami · Milan | USA / France | America/Los_Angeles (PDT) | -3 | Louna | Founder (former top creator) | not published | Supercreator listing → agency site (verify) | verify | Runs the 'Exclu Awards LA' creator event | not published | not published | Founder is the public face; approach via IG DM to Louna + event sponsorship/partnership ask. | 'Exclusive network of international talents'; female-only agency | https://www.supercreator.app/agencies | 1 | 3 | 4 | 4 | 4 | 5 | 78 | 15% | 12:05 | same day |  | Event owner = pitch a TTS award category / live vote at Exclu Awards. Four cities = multi-timezone roster. | Acquirer track — see Acquirers tab
4 | SheX Agency | Germany (DACH) | Germany | Europe/Berlin (CEST) | 6 | Named in Impressum (verify at she-x.de/impressum) | Geschäftsführer (per Impressum) | in Impressum (verify) | she-x.de | @onlyfans_agentur (13K) | Trustpilot 4.8 (132 reviews) | in Impressum (verify) | in Impressum (verify) | German law requires a named responsible person + email + address on the Impressum page — the cleanest direct contact in the whole list. | Claims 450+ staff and 'largest' management for OnlyFans, 4based, BestFans, Fancentro, Maloum (Trustpilot company blurb) | https://ca.trustpilot.com/review/she-x.de · https://www.instagram.com/onlyfans_agentur/ | 1 | 5 | 4 | 4 | 4 | 2 | 79 | 15% | 3:05 | same day |  | Multi-platform (not OF-only) → less TOS-sensitive to off-platform promo. Big DACH roster. Write in English; offer German landing copy. | Acquirer track — see Acquirers tab
5 | Rare X Network / Rare Agency | USA (verify city) | USA | America/New_York (verify) | 0 | not published | — | not published | rareagency.net | verify | — | not published | not published | Matching network that places creators with many agencies — one partnership = multi-agency reach. Approach as co-marketing partner, not as a single agency. | Network of partner agencies; free matching for creators (CreditDonkey review) | https://www.rareagency.net/ · https://www.creditdonkey.com/best-onlyfans-agency.html | 1 | 3 | 3 | 4 | 4 | 2 | 64 | 9% | 9:05 | same day |  | Channel multiplier. Offer: TTS as a perk they hand every placed creator. | Weekly enlistment — demand evidence
6 | Supercreator (software + agency directory) | Israel (directory lists 31 countries) | Israel | Asia/Jerusalem | 7 | not published | Partnerships / community | not published | supercreator.app/agencies · consultation Calendly on site | — | Telegram t.me/supercreator_app · X @Supercreatorapp · podcast on Spotify | not published | not published | Not an agency — the tool 25,000 creators/agencies use. Pitch: partner listing, podcast slot, co-marketing to their agency base. | 25,000 customers claim; directory of verified agencies | https://www.supercreator.app/agencies | 1 | 5 | 4 | 4 | 4 | 2 | 79 | 15% | 2:05 | same day |  | Highest-leverage single relationship: their directory IS the global list. | Acquirer track — see Acquirers tab
7 | Lost Boys Agency | verify (invite-only) | verify | verify | 0 | not published | — | not published | Instagram only | @lostboys.agency | — | not published | not published | Invite-only; IG DM or warm intro only. Do not cold email. | Claims $2M+/mo net sales; one talent $55M in debut year (their own PR) | https://www.instagram.com/lostboys.agency/ · https://secretsofonlyfans.gumroad.com | 1 | 5 | 1 | 3 | 3 | 2 | 57 | 9% | 9:05 | same day |  | Whale roster; low reachability. Worth one IG DM + one warm-intro attempt, then park. | Weekly enlistment — demand evidence
8 | Unruly Agency | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | Tara 'Electra' Niknejad; co-founder Nicky Gathrite | CEO; Co-founder | not published | unrulyagency.com (verify) | verify | — | not published | Not on site — CA SoS bizfile | CEO is named in press; LinkedIn/IG DM. Diligence first (see notes). | 100+ models/influencers, 500M combined reach (2021 BusinessWire) | https://www.businesswire.com/news/home/20210914005352/en/ · https://www.rollingstone.com/culture/culture-news/onlyfans-creators-unruly-agency-nudity-lawsuit-1320185/ | 2 | 4 | 3 | 3 | 2 | 3 | 62 | 9% | 12:05 | same day |  | Multiple creator lawsuits 2021-24; 2026 press releases say all claims dismissed/dropped. Reputation check before any public co-marketing — your 'never be seen as malicious' rule. | Weekly enlistment — demand evidence
9 | Behave Agency | Los Angeles (founded 2020) | USA | America/Los_Angeles (PDT) | -3 | not published | — (Unruly-affiliated) | not published | verify | verify | — | not published | not published | Same diligence as Unruly; contact via Unruly leadership. | Smaller-influencer arm of Unruly (Daily Beast) | https://www.cbinsights.com/company/behave-agency | 3 | 3 | 2 | 3 | 2 | 2 | 49 | 4% | 12:05 | same day |  | Named in the same suits as Unruly. | Weekly enlistment — demand evidence
10 | Sakura Management | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site (verify) | verify | — | not published | not published | Ex-webcam traffic firm → performance-marketing mindset; pitch the funnel math. | 5+ yrs; adult + mainstream creators (Supercreator listing, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 4 | 4 | 3 | 67 | 15% | 12:05 | same day |  | Traffic-ops DNA = understands CAC/LTV pitch. | Weekly enlistment — demand evidence
11 | Doris Agency / Doris Talent | Los Angeles · Miami | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site (verify) | verify | — | not published | not published | Site contact + IG DM. | Production company + influencer marketing (Supercreator, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 3 | 4 | 3 | 63 | 9% | 12:05 | same day |  | Brand-partnership oriented — frame TTS as a sponsor-ready property. | Weekly enlistment — demand evidence
12 | Seiren | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | verify | verify | — | not published | not published | Site form + IG. | Claims 'most of the top 1% creators' (Vocal Media roundup) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 4 | 2 | 3 | 4 | 3 | 63 | 9% | 12:05 | same day |  | Safety/comfort-first positioning — lead with consent agreement + no-OF-posting. | Weekly enlistment — demand evidence
13 | Teasy Agency | USA (verify city) | USA | verify (assume ET) | 0 | Co-founded by a female creator (name not published) | Co-founder | not published | teasyagency.com | verify | — | not published | not published | Site form; ask for co-founder by role. | Creator-founded; multi-tier management (site) | https://teasyagency.com/ | 2 | 3 | 3 | 3 | 4 | 2 | 60 | 9% | 9:05 | same day |  | Creator-led leadership responds to creator-benefit framing (trophies, weekly spotlight). | Weekly enlistment — demand evidence
14 | Think Expansion | Miami, FL | USA | America/New_York (EDT) | 0 | not published | — | not published | verify | verify | — | not published | not published | Site form. | 'One of the first OF agencies'; no-face/discreet models (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 2 | 4 | 3 | 59 | 9% | 9:05 | same day |  | Discreet roster = lower fit for a public photo leaderboard. Offer masked/creative-profile option or deprioritize. | Weekly enlistment — demand evidence
15 | Emerald Agency | Gold Coast, AU · Los Angeles | Australia / USA | Australia/Brisbane (AEST, no DST) | 14 | not published | — | not published | verify | verify | — | not published | not published | Site form; NYT Magazine feature gives a PR-savvy hook. | NYT Magazine-featured; exclusive roster (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 3 | 4 | 3 | 63 | 9% | 19:05 | previous day (ET) |  | Dual timezone: send AU batch and LA batch separately. | Weekly enlistment — demand evidence
16 | Aruna Talent | verify country | verify | verify | 0 | not published | — | not published | arunatalent.com (apply) | verify | — | not published | not published | Site apply page + LinkedIn search 'Aruna Talent'. | 60+ creators, ~100-person team, $10M+/yr creator revenue (their own 'State of OnlyFans 2026' post) | https://arunatalent.com/blog/state-of-onlyfans-2026/ | 2 | 4 | 3 | 3 | 4 | 2 | 65 | 15% | 9:05 | same day |  | Publishes industry data — data-driven; send the EV calculator. | Weekly enlistment — demand evidence
17 | TDM Agency | verify (worldwide) | verify | verify | 0 | not published | — | not published | tdmmanagement.com | verify | — | not published | not published | Site form; Supercreator-verified listing. | 'World's leading' claim (Supercreator listing) | https://tdmmanagement.com/ · https://www.supercreator.app/agencies | 2 | 4 | 3 | 3 | 4 | 3 | 68 | 15% | 9:05 | same day |  | Cross-creator collab culture = weekly contest fits their playbook. | Weekly enlistment — demand evidence
18 | FansHub | UK & USA chat teams | UK / USA | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; Companies House for UK Ltd officers. | 20+ promo methods incl. meme pages, podcasts, influencer collabs (Talented Ladies Club) | https://www.talentedladiesclub.com/articles/five-best-onlyfans-management-agencies-in-2026/ | 2 | 3 | 3 | 4 | 4 | 2 | 64 | 9% | 4:05 | same day |  | Marketing-native — TTS is one more promo method for their stack. | Weekly enlistment — demand evidence
19 | Lush Management | UK HQ; roster US/UK/AU | UK | Europe/London (BST) | 5 | not published | — | not published | lushmgmt.co.uk/apply (form) | @thelushmgmt | X @lush_mgmt | not published | not published | Form + X/IG DM; Companies House for directors. | 'Nearly three years' experience; performance-only fees (site) | https://www.lushmgmt.co.uk/ | 2 | 3 | 3 | 3 | 4 | 2 | 60 | 9% | 4:05 | same day |  | Publishes Twitter/Reddit promo guides — comfortable with off-platform promo. | Weekly enlistment — demand evidence
20 | Rize Agency | UK | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; Companies House. | Claims $5k→$180k/mo client growth (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 2 | 3 | 4 | 2 | 55 | 9% | 4:05 | same day |  |  | Weekly enlistment — demand evidence
21 | Elite OnlyFans Management | Australia · UK · Dubai | AU / UK / UAE | Asia/Dubai (GST) | 8 | not published | — | not published | eliteonlyfansmgmt.com (apply) | verify | — | not published | not published | Site form. | International team; ex-top-0.1% creators (site) | https://www.eliteonlyfansmgmt.com/ | 2 | 3 | 3 | 4 | 4 | 3 | 67 | 15% | 1:05 | same day |  | Dubai presence = crypto-comfortable. | Weekly enlistment — demand evidence
22 | Bunny Studios (Bunny Agency) | Germany (est. 2019) | Germany | Europe/Berlin (CEST) | 6 | Named in Impressum (verify) | Geschäftsführer | in Impressum (verify) | bunny-studios.com | @onlybunnyagency | — | in Impressum | in Impressum | Impressum. Confirm whether the Supercreator 'Bunny agency' listing is the same entity. | 'Top one OF agency in Europe' claim; no lock-in contracts (site) | https://bunny-studios.com/ · https://www.supercreator.app/agencies | 2 | 3 | 4 | 3 | 4 | 2 | 65 | 15% | 3:05 | same day |  |  | Weekly enlistment — demand evidence
23 | NEO Agency | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | in Impressum | in Impressum | Impressum. | AI-driven growth positioning (Vocal Media) | https://vocal.media/filthy/top-10-best-only-fans-agencies-2024 | 2 | 3 | 4 | 4 | 4 | 2 | 69 | 15% | 3:05 | same day |  | Tech-forward — onchain trophies/gasless wallets are a feature. | Weekly enlistment — demand evidence
24 | NorthCoast Agency | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | in Impressum | in Impressum | Impressum. | '$6M+ earned for creators' claim (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 4 | 3 | 4 | 2 | 65 | 15% | 3:05 | same day |  |  | Weekly enlistment — demand evidence
25 | Dolce Vita Agency | USA & Germany teams | USA / Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | verify | verify | — | not published | not published | Impressum (if DE entity) or site form. | 25+ creators, most top 0.02% (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  | 'No PPV spam' ethos — lead with fan-experience framing. | Weekly enlistment — demand evidence
26 | Foxy Studios | EU (verify country; euro-denominated) | verify | Europe/Berlin (assume CEST) | 6 | not published | Female-led leadership team | not published | Supercreator listing → site | verify | — | not published | not published | Site/Impressum. | 55/45 split in creator's favor; real-time dashboards (Supercreator, verified) | https://www.supercreator.app/agencies | 2 | 3 | 3 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  | Transparency brand — show the onchain audit page and prize split. | Weekly enlistment — demand evidence
27 | Magic Agency | verify (hosts meetups in USA, Thailand, Dubai, Europe, Brazil) | verify | verify | 6 | not published | — | not published | verify | verify | — | not published | not published | Site form; ask to attend a meetup. | Global creator meetups; weekly QA reports (Vocal Media) | https://vocal.media/journal/11-best-only-fans-agencies-to-join-best-only-fans-management-and-marketing-agencies-to-join-as-a-creator | 2 | 3 | 3 | 4 | 4 | 4 | 70 | 15% | 3:05 | same day |  | Meetup culture = in-person pitch to founder + creators at once. | Weekly enlistment — demand evidence
28 | Upbrand | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | Tony Izzet | Founder | not published | Instagram | @upbrand.au (121K) · founder @tonyizzet | — | not published | not published | Founder is public on IG — DM him directly. ABN Lookup for the entity. | 'Scaling models globally to $40,000+/mo'; 'all spots currently filled' (IG bio) | https://www.instagram.com/upbrand.au/ | 2 | 3 | 4 | 3 | 4 | 2 | 65 | 15% | 19:05 | previous day (ET) |  | 'Spots filled' = capacity-constrained; TTS adds revenue without adding headcount. | Acquirer track — see Acquirers tab
29 | Azzur Agency (OnlyFansManagement.com.au) | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | Leadership roles on About page (names: verify) | not published | onlyfansmanagement.com.au/about-us | verify | — | not published | not published | About page lists roles; ABN Lookup. | Talent/celebrities/public figures focus (site) | https://onlyfansmanagement.com.au/ | 2 | 3 | 3 | 3 | 4 | 2 | 60 | 9% | 19:05 | previous day (ET) |  | Celebrity roster = bigger vote pull per creator. | Weekly enlistment — demand evidence
30 | SirenCY | verify (CY?) | verify | Europe/Nicosia (assume EEST) | 7 | not published | — | not published | sirency.com | verify | — | not published | not published | Site; treat their numbers as marketing until verified. | Claims 312+ creators, $50M+ managed (own blog) | https://www.sirency.com/blog/biggest-onlyfans-agencies-2026-the-major-players-revealed | 2 | 4 | 3 | 3 | 3 | 2 | 62 | 9% | 2:05 | same day |  | Verify before relying on scale. | Weekly enlistment — demand evidence
31 | Melossom Management | UK | UK | Europe/London (BST) | 5 | not published | — | not published | melossommgmt.com | verify | — | not published | not published | Site form; Companies House. | 'UK's leading' claim (site) | https://www.melossommgmt.com/ | 3 | 2 | 2 | 3 | 4 | 2 | 50 | 9% | 4:05 | same day |  |  | Weekly enlistment — demand evidence
32 | Red Fox | UK | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form. | Custom packages; copywriters/analysts (AROA UK roundup) | https://aroaagency.com/uk/blog/the-biggest-best-onlyfans-agencies | 3 | 2 | 2 | 3 | 4 | 2 | 50 | 9% | 4:05 | same day |  |  | Weekly enlistment — demand evidence
33 | Everlasting Eros / EROS Agency | London | UK | Europe/London (BST) | 5 | not published | — | not published | verify | verify | — | not published | not published | Site form; confirm whether EROS Agency is the same firm. | Brand-strategy-first positioning | https://www.laxir.us/single-post/top-5-best-onlyfans-agencies-management-services | 3 | 2 | 2 | 3 | 4 | 2 | 50 | 9% | 4:05 | same day |  |  | Weekly enlistment — demand evidence
34 | 20MG (Twenty Management Group) | USA-registered; serves US/UK/AU/CA | USA | America/New_York (assume EDT) | 0 | not published | — | not published | 20mg.co (apply) | verify | — | not published | not published | Site form. | Small deliberate roster; six-figure marketing budgets claim (site) | https://20mg.co/ | 3 | 2 | 3 | 3 | 4 | 2 | 55 | 9% | 9:05 | same day |  | Serves Canada — CASL: no cold email to Canadian contacts; use form/DM. | Weekly enlistment — demand evidence
35 | Xcelerate Agency | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | AI + social-media-marketing positioning (Supercreator, verified) | https://www.supercreator.app/agencies | 3 | 2 | 3 | 4 | 4 | 2 | 59 | 9% | 12:05 | same day |  |  | Weekly enlistment — demand evidence
36 | 2TWENTYTWO | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Boutique, premium chatting (Supercreator, verified) | https://www.supercreator.app/agencies | 3 | 2 | 2 | 3 | 4 | 2 | 50 | 9% | 12:05 | same day |  |  | Weekly enlistment — demand evidence
37 | WE ARE VERIFIED | Los Angeles | USA | America/Los_Angeles (PDT) | -3 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Talent-first management (Supercreator listing) | https://www.supercreator.app/agencies | 3 | 2 | 2 | 3 | 4 | 2 | 50 | 9% | 12:05 | same day |  |  | Weekly enlistment — demand evidence
38 | Verge Agency | verify | verify | verify | 0 | not published | — | not published | Supercreator listing → site | verify | — | not published | not published | Site form. | Models, influencers, celebrities (Supercreator listing) | https://www.supercreator.app/agencies | 3 | 3 | 2 | 3 | 4 | 2 | 55 | 9% | 9:05 | same day |  |  | Weekly enlistment — demand evidence
39 | OFM (of-management.com) | Nuremberg, Germany | Germany | Europe/Berlin (CEST) | 6 | Two brothers (names in Impressum — verify) | Founders | in Impressum (verify) | of-management.com | verify | — | in Impressum | in Impressum | Impressum. | Ex-B2B social agency turned OFM (site) | https://www.of-management.com/ | 3 | 2 | 4 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  | B2B-marketing roots — will read an EV model. | Weekly enlistment — demand evidence
40 | Adler Agency | Germany (DACH, since 2024) | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | adleragency.de | verify | — | in Impressum | in Impressum | Impressum. | Selected models and agencies in DACH + worldwide (site) | https://www.adleragency.de/en | 3 | 2 | 4 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  | Works with other agencies — possible sub-network. | Weekly enlistment — demand evidence
41 | FameGrowth | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | famegrowth.de | verify | — | in Impressum | in Impressum | Impressum. | 8+ yrs experience claim (site) | https://famegrowth.de/en | 3 | 2 | 4 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  |  | Weekly enlistment — demand evidence
42 | MAHO Management | DACH | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | maho-management.com | verify | — | in Impressum | in Impressum | Impressum. | Brand management + Instagram/TikTok/Twitch promo (site) | https://maho-management.com/en/ | 3 | 2 | 4 | 4 | 4 | 2 | 64 | 9% | 3:05 | same day |  | Twitch/streamer crossover — gaming-literate roster. | Weekly enlistment — demand evidence
43 | FEM Management | DACH | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | fem-management.com | verify | — | in Impressum | in Impressum | Impressum. | 24/7 DE/EN chat teams; leak protection (site) | https://www.fem-management.com/ | 3 | 2 | 4 | 3 | 4 | 2 | 60 | 9% | 3:05 | same day |  |  | Weekly enlistment — demand evidence
44 | Die OnlyFans Agentur | Germany | Germany | Europe/Berlin (CEST) | 6 | Impressum (verify) | — | in Impressum (verify) | die-onlyfans-agentur.de | verify | — | in Impressum | in Impressum | Impressum. | — | https://www.die-onlyfans-agentur.de/ | 3 | 2 | 4 | 3 | 3 | 2 | 57 | 9% | 3:05 | same day |  |  | Weekly enlistment — demand evidence
45 | Prosper Talent Management | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | prospermanagement.com.au | verify | — | not published | not published | Site form; ABN Lookup. | Performance-driven; hiring chat/ops staff (site) | https://www.prospermanagement.com.au/ | 3 | 2 | 3 | 3 | 4 | 2 | 55 | 9% | 19:05 | previous day (ET) |  |  | Weekly enlistment — demand evidence
46 | Flair Management | Sydney | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | flair-management.com | verify | — | not published | not published | Site form. | — | https://flair-management.com/ | 3 | 2 | 3 | 3 | 4 | 2 | 55 | 9% | 19:05 | previous day (ET) |  |  | Weekly enlistment — demand evidence
47 | Nest Talent Pty Ltd | Brisbane | Australia | Australia/Brisbane (AEST, no DST) | 14 | not published | — | not published | nesttalent.com | verify | — | not published | not published | Site form; ASIC/ABN for Pty Ltd officers. | Registered company; performance-based offer (site) | https://www.nesttalent.com/ | 3 | 2 | 3 | 3 | 4 | 2 | 55 | 9% | 19:05 | previous day (ET) |  |  | Weekly enlistment — demand evidence
48 | Aura Management | Australia | Australia | Australia/Sydney (AEST→AEDT Oct 4) | 14 | not published | — | not published | auramgmt.com.au | verify | — | not published | not published | Site form. | Traditional talent-management ethos; also non-female creators (site) | https://www.auramgmt.com.au/ | 3 | 2 | 3 | 3 | 4 | 2 | 55 | 9% | 19:05 | previous day (ET) |  |  | Weekly enlistment — demand evidence
49 | OFM Models (ofmmodels.com) | verify (Telegram-first) | verify | verify | 6 | not published | — | not published | ofmmodels.com | verify | Telegram @ofmm_agency | not published | not published | Telegram DM. | Serves Japanese creators too; Telegram intake (site) | https://ofmmodels.com/en/blog/kto-sozdal-onlyfans | 3 | 2 | 4 | 4 | 3 | 1 | 58 | 9% | 3:05 | same day |  | Telegram-native — TTS bot integration is a natural fit. | Weekly enlistment — demand evidence
50 | Bop House (creator collective — not an agency) | Miami, FL | USA | America/New_York (EDT) | 0 | Managed collective | — | not published | via their management / Creators Inc relationship | verify | — | not published | not published | Reach through Creators Inc — not directly. | Highest-profile OF creator house (Wikipedia) | https://en.wikipedia.org/wiki/Bop_House · https://www.creatorsinc.com/ | 2 | 5 | 1 | 2 | 3 | 3 | 56 | 9% | 9:05 | same day |  | Warm intro only. | Weekly enlistment — demand evidence
51 | LONG TAIL — Supercreator directory (31 countries, paginated) | Serbia, Estonia, Slovenia, DR, Israel, Italy, UAE, Turkey, NL, Poland, Brazil, Canada, France, Ukraine, Sweden, Czechia, Bali, Argentina, India, Switzerland, Colombia, Bulgaria, Belgium, Costa Rica, Mexico, Spain… | Global | varies | 0 | — | — | — | https://www.supercreator.app/agencies (filter by country/city) | — | — | — | — | Work page by page; each listing links to the agency site → Impressum/contact/footer. | Directory of listed agencies (some verified by Supercreator) | https://www.supercreator.app/agencies | 3 | 3 | 3 | 3 | 3 | 2 | 57 | 9% | 9:05 | same day |  | Batch 10-15 new rows per week from here; keep the same scoring. | Weekly enlistment — demand evidence
| Expected meetings from this list (sum of P(meeting), full multi-channel sequence) | [22 empty] | 5.48
| Tier-1 / Tier-2 / Tier-3 count | [15 empty] | 7 / 23 / 21
Component scores (cols S-W) are analyst estimates from public info. Offsets: UK/EU clocks fall back Oct 25, US Nov 1, Sydney springs forward Oct 4 — recheck send times after those dates.

## Events & Hangouts
Where buyers and agency owners are — business venues only
Event / venue | City | Dates | Who you'll meet | The play | Status | Source
XBIZ Show / XBIZ Week (+ X3 Expo, XMAs) | Los Angeles | Jan 7-10, 2027 | Agency execs, platform reps, performers, marketers; AROA exhibits/attends | Book business-lounge meetings from the target list; demo the weekly vote on a tablet | Dates confirmed on xbizshow.com (Sept 19 check) | https://www.xbizshow.com/
AVN Adult Entertainment Expo + AVN Awards | Las Vegas | Late Jan 2027 (confirm) | Largest consumer+trade adult expo; agencies scout talent | Booth-side weekly-vote demo | Confirm on avn.com | https://avn.com/
Rick's Cabaret New York (RCI Hospitality) | NYC - 50 W 33rd St | Any evening (call ahead) | Venue GM; RCI has hosted investor meet-ups here | 60-second /clubs demo + ask for a corporate intro | Business venue | RCI earnings call transcript
NJ clubs on your /clubs list | New Jersey | Oct 8 evening (Plan tab) | Owners/GMs | Sign up 2-3 clubs on the spot = demand evidence | Your list | -
Miami Swim Week — CI Swimwear (Creators Inc) | Miami | Late May / early June (confirm) | Andy Bachman + roster | Gifting-suite slot = time with the #1 target's founder | Confirm | https://www.creatorsinc.com/
Exclu Awards LA (Louna's Models) | Los Angeles | Confirm with Louna's | Top creators + Louna | Propose a TTS-powered fan-vote award | Confirm | https://www.supercreator.app/agencies
Exxxotica Expo | Edison NJ · Chicago · DC · Miami | Confirm 2026-27 dates | Creators, fans, some agency managers | Creator signup drive on home turf | Confirm | https://en.wikipedia.org/wiki/Exxxotica_Expo
Creators Inc podcast | Online | Weekly | Andy Bachman | Pitch yourself as a guest (pro-sports S&C coach + Prime documentary + creator economy) | Open | https://www.creatorsinc.com/
Supercreator Telegram + podcast | Online | Ongoing | Agency owners | Partner listing / guest slot | Open | https://www.supercreator.app/agencies
LinkedIn | Online | Daily | Founders/CEOs on the Acquirers tab | Connect note, then Email 2 content as a message | Open | -

## Agency EV Calculator
What TTS is worth to an agency — plug their numbers in on the call (inputs blue/yellow; outputs are formulas)
Frame: TTS is a zero-labor top-of-funnel. Each creator on the weekly board gets a profile that routes voters to her link hub. Token prizes are upside — enter 0 unless you have the verified figure.
INPUTS
Weekly active voters on the board (YOUR live number — replace) | 1000 | Pull from admin; example value only
Creators on the board in a typical round | 30 | Example value
Share of voters who view a given creator's profile | 20% | Assumption — measure in-app
Profile → link-hub click-through | 10% | Assumption — add UTM to each hub link and measure
Link-hub → paid subscription conversion | 3% | Assumption; agencies know their own number — ask
Average subscription price ($/mo) | 10 | Agency input
Platform fee (OnlyFans keeps 20%) | 20% | OnlyFans standard split
Agency share of creator NET revenue | 40% | Industry range roughly 20-50% — agency input
Average months a new sub stays | 2.5 | Agency input
Agency labor per creator per week (hours) to participate | 0.25 | Uploading a photo + posting the vote link
Agency labor cost ($/hour) | 20 | Agency input
Creators the agency enters per week | 10 | The ask
Expected token/prize value per creator per week ($) — VERIFIED figure only, else 0 | 0 | Leave 0 until the prize split is confirmed; never promise a pool size
Fans each entered creator brings in as voters per week | 50 | Assumption — the network effect: every roster brings its own voters
Share of those fans who sign up through the agency's referral link | 30% | Assumption
Referral payout per referred signup (TTS) — VERIFIED figure only, else 0 | 0 | Verify in admin before quoting
TTS price used for valuation ($) — pool-realizable price, else 0 | 0 | Only value what the pool can absorb
OUTPUTS (per creator per week unless stated)
Effective weekly voters (base + fans the entered creators bring) | 1500
Profile views per creator per week | 300
Link-hub clicks per creator per week | 30
New paid subs per creator per week | 0.9
Creator gross from those subs over their lifetime ($) | 22.5
Creator net after platform fee ($) | 18
Agency revenue from those subs ($) | 7.2
Agency labor cost per creator per week ($) | 5
Agency net per creator per week, subs only ($) | 2.2
Agency referral revenue per creator per week ($) | 0
Agency net per creator per week incl. referral + verified prize share ($) | 2.2
Agency weekly net for the creators entered ($) | 22
Agency annualized net ($) — 52 rounds | 1144
Break-even link-hub→sub conversion (labor covered, subs only) | 2.083%
Return on labor (net ÷ labor cost) | 0.44
How to use on a call: ask for THEIR sub price, agency share and hub→sub conversion, leave the TTS-side assumptions as-is, and read rows 35-36 back to them. If row 37 (break-even conversion) is below their real conversion, participation pays at zero prize value.